## Initiatives and Components List
Initiative
Component
Subcomponent
I. | Chronic Care Innovation (CCI): Rural Community Hubs, Community Health Workers, and Data and Technology Strategies
I.a | Rural Community Hubs (RCH)
I.a.1 RCH Convening Organization
I.a.2 RCH Lead Organizations
i. Pilot RCH Lead Organizations
ii. RCH Roll Out across Kentucky
I.a.3 Locally Led Initiatives
1.a.4 Community Collaboration Workspace enhancement developed with Vitality Signs
I.b | Food and Nutrition
I.c | Workforce
I.c.1 Foundational CHW Training
I.c.2 Specialized Certificates for CHWs
I.c.3 CHW Sustainability Education
I.c.4 Health Care Workforce Pipeline
I.d | Data and Technology Strategy
I.d.1 Community Collaboration Hub (Vitality Signs)
i. RCH Partner Collaboration Workspace enhancement developed with RCH
I.d.2 Community Care Coordination
i. Kentucky Health Information Exchange
ii. kynect resources
I.d.3 Knowledge and Insights Infrastructure
I.d.4 Consumer-Facing Technology (activities deferred pending input from stakeholders)
I.d.5 Learning Health System
II. | Maternal and Infant Health: Community-Based PoWER Teams
II.a | Pre-Pregnancy Community Education and Awareness
II.a.1 Community-Based Maternal Health Councils
II.b | PoWER-Supported Maternity Care
II.b.1 Electronic Report of Pregnancy (eROP) and Electronic Perinatal Risk Assessment Form (ePRAF)
II.b.2 Prenatal Oral Health Testing
II.b.3 Level II/III Fetal Ultrasonography and Maternal Fetal Medicine (MFM) Telehealth Consultation
II.c | Workforce
II.c.1 Train PoWER Teams and Community Partners on the PoWER Care Model
II.c.2 Doula Workforce Development and Expansion
II.c.3 Training Frontline Workers on Maternity and Infant Care
II.c.4 Community Health Worker Training on Maternity Care
II.c.5 HANDS Expansion
II.c.6 Health Care Workforce Pipeline
III. | Behavioral Health: Rapid Response to Recovery (R3) - EmPATH Model, Crisis Response, and Telebehavioral Health Hub
III.a | Scale EmPATH
III.b | Technology to Improve the Behavioral Health Care Continuum
III.b.1 Telebehavioral Health Hub to Support Behavioral Health Care Delivery
i. Pathway 1: On-Demand Crisis Care Platform
ii. Pathway 2: Collaborative Care Model (CoCM)
III.b.2 Crisis Reponse Technology for calls to 988
III.c | CMHCs to Support EmPATH and Community-Based Crisis Support Programs
III.d | CMHCs to Pilot 202a and Crisis Transportation Intervention Strategies
III.e | Workforce
III.e.1 First Responder Training, Technical Assistance, and Relationship Building
III.e.2 Health Care Workforce Pipeline
IV. | Oral Health: Rooted in Health (RiH) - Kentucky Rural Dental Access Program
IV.a | Workforce
IV.a.1 New or Expanded Accredited Dental Hygiene Programs
IV.a.2 Dental Assistant Workforce Expansion
IV.a.3 Advanced Dental Extraction Training for Rural Dentists
IV.a.4 Advanced Education in General Dentistry
IV.a.5 Dental Training Equipment and Content Development
IV.a.6 Health Care Workforce Pipeline
IV.b | Teledental Hubs
IV.c | Public Health Dental Hygiene Services
IV.c.1 Increase the Number of New or Expanded Teams
IV.c.2 Expand Scope to Long-Term Care Settings
IV.d | Definitive Dental Care Services
IV.d.1 Mobile Dental Units for Definitive Care
i. Increase Hook Up Ready Locations for Mobile Dental Units
IV.d.2 Fixed-Site Access Points for Definitive Care
IV.d.3 Rural Dental Emergency Access Network
V. | EMS and Trauma: Crisis to Care (CTC) - Integrated EMS and Trauma Response
V.a | Workforce
V.a.1 EMS Education & Training (E&T) Modernization
V.a.2 Paramedic Training
V.a.3 Mobile Training Facility
V.a.4 Health Care Workforce Pipeline
V.b | Community Paramedicine Programs
V.c | Treat No Transport (TNT) and Transport to Alternative Destination (TAD)
V.d | Regional Medical Operations Coordination Centers (RMOCC)
V.e | Special Needs Tracking and Awareness Response System (STARS) for Children with Special Health Care Needs

## I. CCi Project Plan
| Initiative I: Chronic Care Innovation (CCi): RCHs, CHWs, and Data and Technology Strategy | Key |  | Status Report
|  | Stage | 74 | Complete
| Designated Leads: RCH: Allison Adams; CHWs: Ashley Gibson; Data/Tech: Deepak Mirchanani | Milestone | 12 | In Progress - On Track
|  | Task | 1 | In Progress - Behind Schedule
|  |  | 78 | Not Yet Started
|  |  | 0 | Upcoming
Milestones in red font have been completed
Checkpoints highlighted in yellow have been met
Stage | Milestones/Tasks | Target Start | Target Due Date | Status Report | Task Owner | Notes
Component |  |  |  | as of 7/31/2026 |  | Documentation is provided in the Checkpoint Evidence Attachment (CEA)
Stage 0 | Planning
I | Stand Up CCi Teams for RCH, CHWs, and Data/Technology | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Confirm Convening Organization | 2026-01-01 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| Select staffing mechansim(s) | 2026-01-01 | 2026-02-01 | Complete | Dr. John Langefeld, Andrew Yunt
| Establish CHFS internal advisors for CCI | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Kickoff Meeting with A3 leadership team, key partners, and support team (all five initiatives) | 2026-01-06 | 2026-01-06 | Complete | Dr. John Langefeld, Tom Walton
| ADD selection criteria discussion (all initiatives) | 2026-02-19 | 2026-02-19 | Complete | Dr. Brent Wright, Andrea Adams
| CCI stakeholder engagement strategy meeting (internal) | 2026-01-30 | 2026-01-30 | Complete | Andrew Bledsoe
| UK CPH meeting re: Partner Tool and measuring strength of local networks | 2026-02-05 | 2026-02-05 | Complete | Allison Adams
| Checkpoint 0.1 Establish governance |  |  |  |  | See Initiative Organization Chart, Role Descriptions and Staff Bios in CEA
I | Establish Governance | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Define initiative team operating model and governance structure | 2026-01-01 | 2026-01-27 | Complete | Dr. John Langefeld, Tom Walton
| Establish approval processes and operational decision flows for initiative design, budget, and execution | 2026-02-10 | 2026-05-20 | Complete | Dr. John Langefeld, Tom Walton
| Establish regular cadence for RHT financial reporting | 2026-02-09 | 2026-05-31 | Complete | Dr. John Langefeld, Tom Walton
| Procure and launch PM tool for initiative tracking and collaboration | 2026-04-02 | 2026-07-30 | Complete | Dr. John Langefeld, Tom Walton
| Compliance sprint to inform the development of the RHT subrecipient risk assessments process and monitoring plan | 2026-06-02 | 2026-06-30 | Complete | Dr. John Langefeld, Tom Walton
Checkpoint 0.2 Submit project plan to CMS
I | Develop Project Plan |  |  | In Progress - Behind Schedule | All Leads | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Refine milestones and flesh out acitvities in project plan | 2026-01-01 | 2026-06-26 | Complete | All Leads
| Submit project plan to CMS for informal review | 2026-06-29 | 2026-07-15 | Complete | Andrea Adams | submitted 7/30/2026
| Dialogue with CMS re: project plan | 2026-08-07 | 2026-08-31 | In Progress - On Track | Leadership Team
| Revise project plan based on CMS feedback | 2026-08-07 | 2026-08-31 | In Progress - On Track | Andrea Adams, All Leads
| Submit revised project plan to CMS | 2026-08-18 | 2026-08-31 | In Progress - On Track | Andrea Adams
Stage 1 | Initial Launch (public announcement or at least one contract signed or sub-recipient selected) |  |  | In Progress - On Track
Checkpoint 1.1 CMS approval of project plan
I | Receive approval of project plan from CMS | 2026-07-15 | 2026-07-31 | Not Yet Started |  | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Checkpoint 1.2 Launch initiative |  |  |  |  | See Stakeholder Engagement section of CEA
I | Launch Initiative I (CCi): Engage Stakeholders and/or Establish Advisory Groups | 2025-12-29 | 2026-07-31 | Complete | Executive Team, Allison Adams | Checkpoint 2.2 Achieve at least one post-launch milestone
| Press Release re: Kentucky RHT funding | 2025-12-29 | 2025-12-29 | Complete | Governor's Office | kentucky.gov/Pages/Activity-stream.aspx?n=GovernorBeshear&prId=2666
| KyRHT appearances before the Kentucky Legislature during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Project Sponsor and RHT Director testify before the Senate Standing Committee on Health Services | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| RHT Director testifies before the Interim Joint Budget Review Subcommittee of Health and Family Services Committee | 2026-06-03 | 2026-06-03 | Complete | Tom Walton
| RHT Director testifies before the Interim Joint Committee on Health Services | 2026-06-16 | 2026-06-16 | Complete | Tom Walton
| Working session re: Chronic Care Innovation initiaitve vision and approach to care cordination | 2026-01-15 | 2026-01-15 | Complete | Dr. John Langefeld, Tom Walton
| Develop "Jane's Journey" for CCi Initiative | 2026-02-20 | 2026-03-30 | Complete | Jessi Watts, Allison Adams, Team
| Develop and finalize 1-page RCH handout for stakeholder meetings and conferences | 2026-04-01 | 2026-05-15 | Complete | Jessi Watts, Allison Adams | Included in CEA
| Stakeholder Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Dr. Connie White, Dr. Alisha Morgan | Details provided with Checkpoint Evidence
| Stakeholder Engagement during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Jessi Watts, Drs. White and Morgan | Details provided with Checkpoint Evidence
| First meeting of CHW Advisory Group | 2026-06-24 | 6/24/20/26 | Complete | Ashley Gibson | 9 organizations represented
| Food is Medicine Forum (internal and external S/Hs) | 2026-07-15 | 2026-07-15 | Complete | Dr. Brent Wright
| AFFI meeting | 2026-02-27 | 2026-02-27 | Complete | Dr. Brent Wright
| KPCA kynector and CHW Roundtable | 2026-03-12 | 2026-03-12 | Complete | Ashley Gibson
| Local World Champions | 2/29/2026 | 2/29/2026 | Complete | Tom Walton
Stage 2 | Early Scale
| Checkpoint 2.1 Continue initiaitve activities (implementation) |  |  |  |  | Please consider this project plan as evidence for conitinued activites after CCi Initiaitve Launch
I.a | Select Convening Organization (Tier 1 Subrecipient) to Establish and Support RCHs across Kentucky | 2026-01-12 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton | Checkpoint 2.2 Achieve at least one post-launch milestone
| Submit convening organization subrecipient budget to CMS | 2026-01-12 | 2026-01-30 | Complete | Tom Walton, Andrew Yunt
| Receive NOA (including subrecipient budget) | 2026-01-30 | 2026-02-05 | Complete | Tom Walton, Andrew Yunt
| Announce convening organization (Senate Standing Committee on Health Services on 2/18) | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton | Convening Organization Subrecipient announced
| Initial work planning, team structure, and stakeholder engagement | 2026-01-05 | 2026-03-15 | Complete | Allison Adams
I.a.1 | Select RCH Lead Organizations (Tier 2 Subrecipients) for each Pilot ADD | 2026-02-18 | 2026-07-31 | Complete | Allison Adams | Checkpoint 2.2 Achieve at least one post-launch milestone
| Develop approach and methodology for pilot prioritization | 2026-02-02 | 2026-02-20 | Complete | Allison Adams
| Finalize pilot prioritization approach | 2026-02-20 | 2026-02-20 | Complete | Allison Adams
| Select pilot ADDs | 2026-03-15 | 2026-03-15 | Complete | Allison Adams | Purchase, Lake Cumberland, and Big Sandy ADDs selected
| Facilitate RCH information sessions | 2026-04-20 | 2026-04-20 | Complete | Allison Adams
| Develop and release RFA (selection of RCH Lead Organizations in each pilot ADD) | 2026-03-10 | 2026-04-21 | Complete | Allison Adams
| Release RFA FAQs | 2026-05-05 | 2026-05-05 | Complete | Allison Adams
| Applications closed | 2026-06-01 | 2026-06-01 | Complete | Allison Adams
| Select one successful applicant for each pilot ADD | 2026-06-15 | 2026-06-15 | Complete | Allison Adams | Purchase: 2 applicants; Lake Cumberland: 3 applicants; Big Sandy: 5 applicants
| Send Notice of Awards (NOA) to selected RCH Lead Organizations in each pilot ADD | 2026-06-15 | 2026-06-30 | Complete | Allison Adams | NoAs went out 6/16/26 to Purchase District Health Dept, Lake Cumberland District Health Dept. and the Mountain Wellness Collaborative; contracts in negotiations
I.a.1 | RCH Hubs active in at least 2 ADDs | 2026-07-01 | 2027-09-30 | Not Yet Started | Allison Adams
| Finalize contracts with RCH Lead Organizations in each pilot ADD | 2026-07-01 | 2026-09-30 | In Progress - On Track | Allison Adams
| Onboard and conduct kickoff sessions with pilot RCH Lead Organizations | 2026-08-15 | 2026-10-15 | Not Yet Started | Allison Adams
| Conduct/support strategic planning in each pilot ADD (with RCH Lead Organization and local partners) | 2026-09-15 | 2026-11-15 | Not Yet Started | Allison Adams
| Review and approve locally-defined initiatives and budgets for pilot RCHs | 2026-10-15 | 2026-12-15 | Not Yet Started | Allison Adams
| Launch locally-defined initiatives in each pilot RCH | 2026-11-15 | 2027-09-30 | Not Yet Started | Allison Adams
I.a.2 | Collect Business Requirements for RCH Partner Collaboration Workspace in collaboration with Vitality Signs | 2026-07-01 | 2027-09-30 | Not Yet Started | Allison Adams
| Conduct meetings with pilot RCH Lead Organizations to inform business requirements to develop an RCH Partner Collaboration Workspace as an enhancement to Vitality Signs functionality | 2026-08-03 | 2026-11-30 | Not Yet Started | Allison Adams, Dr. Sarah Lewis
| Complete business requirements and strategy for RCH Partner Collaboration Workspace | 2026-12-01 | 2026-12-31 | Not Yet Started | Allison Adams, Dr. Sarah Lewis
I.c.1 and I.c.2 | Select CHW Training Partners | 2026-04-24 | 2027-06-30 | In Progress - On Track | Ashley Gibson
| Confirm RCH program requirements for CHW capabilities | 2026-04-24 | 2026-05-15 | Complete | Ashley Gibson
| Finalize RFA scope and timeline | 2026-05-15 | 2026-06-19 | Complete | Ashley Gibson
| Release initial RFA for CHW specialized certificate training | 2026-07-15 | 2026-07-15 | Complete | Ashley Gibson | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| Facilitate information session and office hours for potential partners | 2026-07-16 | 2026-07-24 | Complete | Ashley Gibson
| Application deadline | 2026-08-05 | 2026-08-05 | Not Yet Started | Ashley Gibson
| Finalize CHW specialized certificate training partners | 2026-08-05 | 2026-08-12 | Not Yet Started | Ashley Gibson
I.c.2 | At least two (2) specialized certificate trainings available for certified CHWs | 2026-07-15 | 2027-08-01 | In Progress - On Track | Ashley Gibson
| Develop content | 2026-07-15 | 2027-06-30 | In Progress - On Track | Ashley Gibson
| Obtain approval for CHW specialized certificate training from KOCHW | 2027-06-30 | 2027-06-30 | Not Yet Started | Ashley Gibson
I.c.4 | Select Health Care Workforce Pipeline Partners | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | Checkpoint 2.2 Achieve at least one post-launch milestone
| Select organization(s) to support workforce pipeline in rural areas focusing on KyRHT related positions | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | UK contract started 7/1/2026; UofL contract starts 8/1/2026
I.c.4 | Develop regional tutoring program to suport rural students pursuing health careers | 2026-07-01 | 2027-09-30 | Not Yet Started | Ashley Gibson
| Serve as regional workforce ambassadors by conducting an annual workforce assessment and resource mapping activities to identify workforce gaps, training needs, and opportunities and summarize findings | 2026-07-01 | 2027-09-30 | Not Yet Started | Ashley Gibson
| Develop and provide a free, statewide virtual and/or in-person tutoring program, reaching at least 20 students each, designed to support rural students pursuing health careers by improving academic readiness in science and math prerequisite courses and collect and submit evaluative and participating data | 2026-07-01 | 2027-09-30 | Not Yet Started | Ashley Gibson
I.d.1 | Select Vitality Signs Solution Provider | 2026-03-02 | 2026-07-31 | Complete | Dr. Sarah Lewis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Complete business requirements and strategy for Vitality Signs | 2026-03-02 | 2026-05-18 | Complete | Dr. Sarah Lewis
| Contract with Vitality Signs solution provider | 2026-03-16 | 2026-03-16 | Complete | Tom Walton, Dr. Sarah Lewis
| Vitality Signs solution demo for A3 leadership team and initiaitve leads | 2026-03-19 | 2026-03-19 | Complete | Dr. Sarah Lewis
I.d.1 | Vitality Signs - Beta site go live | 2026-04-01 | 2026-07-31 | Complete | Dr. Sarah Lewis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Measure Development Workshop for Vitality Signs | 2026-05-18 | 2026-05-18 | Complete | Dr. Sarah Lewis
| Beta site live with digital front door | 2026-04-01 | 2026-07-01 | Complete | Dr. Sarah Lewis | Screen shots of go live email and beta pages available upon request
| Beta site live with at least one data set or measure for each initiative | 2026-04-01 | 2026-07-31 | Complete | Dr. Sarah Lewis | Screen shots of go live email and beta metrics pages available upon request
I.d.1 | Vitality Signs Build Out | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis
| Beta site live with Community Forum functionality | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis
| Open Vitality Signs to the public and begin collecting feedback | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis
| Define leading and lagging indicators and continue development of OKRs | 2026-08-03 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis
I.d.1 | Vitality Signs - RCH Partner Collaboration Workspace Enhancement in collaboration with RCH | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis
| “Build, buy, or do without” decision re: RCH Partner Collaboration Workspace enhancement to Vitality Signs - recommendation by A3 tech team, decision by A3 executive team in consultation with RCH Convening Organization | 2026-10-01 | 2026-10-01 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Contingent on "build, buy, or do without" decision, Procure technology vendor(s) to support platform development and implementation of Collaboration Portal enhancement | 2026-10-01 | 2026-12-31 | Not Yet Started | Dr. Sarah Lewis, A3 Tech Team, Allison Adams
| Contingent on "build, buy, or do without" decision, In collaboration with the RCH Convening Organization, design, build, and conduct testing for RCH Partner Collaboration Workspace enhancement | 2027-01-04 | 2027-05-31 | Not Yet Started | Dr. Sarah Lewis, A3 Tech Team, Allison Adams
| Contingent on "build, buy, or do without" decision, In collaboration with the RCH Convening Organization, pilot and launch the RCH Partner Collaboration Workspace (MVP) enhancement with RCH Lead Organizations in at least 2 ADDs, incorporating user feedback | 2027-08-03 | 2027-09-30 | Not Yet Started | Dr. Sarah Lewis, A3 Tech Team, Allison Adams
I.d.2 | Select Community Care Coordination Tool(s) | 2026-01-15 | 2026-07-31 | Complete | Andrew Bledsoe | Checkpoint 2.2 Achieve at least one post-launch milestone
| Define requirements and procure solutions for digital tools | 2026-01-15 | 2026-03-15 | Complete | Andrew Bledsoe
| KHIE/CSS overview for A3 leadership | 2026-02-06 | 2026-02-06 | Complete | Andrew Bledsoe
| Brainstorm about potential modifications to kynect resources | 2026-03-04 | 414980 | Complete | All Teams
| Care coordination/management solution demonstrations | 2026-03-09 | 2026-03-10 | Complete | Andrew Bledsoe
| Select care coordination/management solution selection | 2026-03-10 | 2026-05-05 | Complete | Tom Walton
I.d.2.ii | Enhance Community Care Coordination Tool(s) - Phase 1 | 2026-03-16 | 2027-08-31 | In Progress - On Track | Andrew Bledsoe, Wendi Braden
| Collect high-level business requirements and develop strategy to enhance kynect Resources | 2026-03-16 | 2026-06-26 | Complete | Wendi Braden
| Prioritize potential modifications kynect resources | 2026-03-20 | 2026-03-20 | Complete | Wendi Braden, Teams
| Procure vendor to formalize detailed business requirements for kynect resources and make enhancements | 2026-06-26 | 2026-07-31 | Complete | Andrew Bledsoe
| · Discovery and design | 2026-08-01 | 11/31/2026 | Not Yet Started | Andrew Bledsoe, Wendi Braden
| · Development and implementation | 2026-12-01 | 2027-06-30 | Not Yet Started | Andrew Bledsoe, Wendi Braden
| · Go Live | 2027-07-01 | 2027-08-31 | Not Yet Started | Andrew Bledsoe, Wendi Braden
I.d.5 | Create High-Level Framework for Developing Knowledge and Insights Infrastructure/LHS | 2026-01-01 | 2026-07-31 | Complete | Tom Walton, Dr. John Langefeld | Checkpoint 2.2 Achieve at least one post-launch milestone
| Initial Technology Enablement Meeting | 2026-01-28 | 2026-01-28 | Complete | Tom Walton, Dr. John Langefeld
| Interoperability Working Session | 2026-02-16 | 2026-02-16 | Complete | Tom Walton, Dr. John Langefeld
| Executive Team defines high-level strategic vision, principles, capabilities, and enabling data and technology framework for Kentucky's Learning Health System | 2026-06-01 | 2026-07-31 | Complete | Tom Walton, Dr. John Langefeld
I.d.5 | Activate LHS/ Collaborative | 2026-07-01 | 2027-07-31 | In Progress - On Track | Tom Walton, Dr. John Langefeld
| Develop Learning Health System Charter and engage state, provider, academic, community, and other key stakeholders to refine vision and strategic direction, guiding principles, and priority capabilities | 2026-08-01 | 2027-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Knowledge and Insights Infrastructure Current State Assessment and Environmental Scan, including existing assets, capabilities, initiatives, governance, workflows, and identified gaps | 2026-07-01 | 2026-12-31 | Not Yet Started | Polly Mullins-Bentley, Randy McCleese
| Define and obtain stakeholder alignment on desired future-state capabilities for Kentucky's Learning Health System | 2026-09-01 | 2027-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Identify and prioritize 3–5 high-value use cases to demonstrate value, inform capability requirements, and support measurable transformation | 2026-09-01 | 2027-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Knowledge and Insights Infrastructure Future State Assessment, Gap Analysis and Implementation Roadmap | 2027-01-01 | 2027-05-01 | Not Yet Started | Polly Mullins-Bentley, Randy McCleese
| Explore data governance models for Learning Health System including decision rights, accountability, data stewardship, privacy, trust, and cross-organizational governance | 2026-08-01 | 2027-05-01 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Develop data governance framework and establish charter for governing body | 2026-08-01 | 2027-06-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Stakeholder validation and alignment on future-state capabilities, priority use cases, and implementation roadmap | 2026-08-01 | 2027-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
Checkpoint 2.3 Establish Reporting Methodology
| Submit Metric Reporting Methodology Report to CMS | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
| Develop finalized metric approaches including how methodologies are being implemented in practice | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
Checkpoint 2.4 Submit updated project plan to CMS
| Updated Project Plan sent to CMS | 2026-11-01 | 2028-05-30 | Not Yet Started | Andrea Adams
Stage 3 | Implementation Mid-point 2Q28
Checkpoint 3.1 Receive CMS approval of updated project plan
| Updated Project Plan Approved by CMS | 2028-06-01 | 2028-06-30 | Not Yet Started | CMS
Checkpoint 3.2 Complete 2Q28 milestones
I.a | RCH Hubs active in at least 5 ADDs | 2027-10-01 | 2028-09-30 | Not Yet Started | Allison Adams
I.a | Statewide RCH Advisory Work Group Established | 2028-10-01 | 2028-12-31 | Not Yet Started | Allison Adams
I.b.2 | At least two (2) additional specialized certificate trainings available for certified CHWs | 2027-08-15 | 2028-08-01 | Not Yet Started | Ashley Gibson
I.c.1 | Vitality Signs - RCH Partner Collaboration Workspace Enhancement in collaboration with RCH | 2028-10-01 | 2028-12-31 | Not Yet Started | Dr. Sarah Lewis, Allison Adams
| Contingent on "build, buy, or do without" decision, RCH Partner Collaboration Workspace (version 1) in at least 5 ADDs | 2026-10-01 | 2026-12-31 | Not Yet Started | Dr. Lewis, A3 Tech Team, Allison Adams
I.c.2 | Community Care Coordination: Care coordination blueprint (workflow design) | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Andrew Bledsoe
| Develop implementation blueprints for selected priority use cases, including workflow design, required capabilities, existing assets, gaps, stakeholder roles, measures, and implementation approach | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Andrew Bledsoe
I.c.3 | Knowledge and Insights Infrastructure: Connect at least one system using national standards | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Andrew Bledsoe
I.c.3 | Knowledge and Insights Infrastructure: Develop Learning Health System Implementation and Evaluation Strategies | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Define leading indicators, outcome measures, and evaluation approach for priority use cases and Learning Health System capabilities | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Establish an implementation science and continuous learning framework to capture, evaluate, refine, and disseminate lessons learned | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Identify reusable frameworks, playbooks, capability models, and implementation lessons that can inform other states and the Multi-State Rural Health Transformation Learning Collaborative | 2027-08-01 | 2028-06-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
Checkpoint 3.3 Report initial metric progress to CMS
| Initial Metric Progress and/or Reporting Methods Report sent to CMS | 2028-07-01 | 2028-12-30 | Not Yet Started | Dr. Sarah Lewis
Stage 4 | Near Completion
I.a | RCH Hubs in at least 10 ADDs | 2029-10-01 | 2029-12-31 | Not Yet Started | Allison Adams
I.c.1 | Vitality Signs: Continue adding and refining data, measures, and functionality | 2028-07-01 | 2029-07-31 | Not Yet Started | Dr. Sarah Lewis
I.c.1 | Vitality Signs - RCH Partner Collaboration Workspace Enhancement in collaboration with RCH | 2028-10-01 | 2028-12-31 | Not Yet Started | Dr. Sarah Lewis, Allison Adams
| Contingent on "build, buy, or do without" decision, Community Collaboration Workspace (version 1) in at least 10 ADDs | 2028-07-01 | 12//31/2028 | Not Yet Started | Allison Adams
I.c.3 | Knowledge and Insights Infrastructure: Connect at least one additional system using national standards | 2028-07-01 | 2029-07-31 | Not Yet Started | Tom Walton and Andrew Bledsoe
I.c.3 | Knowledge and Insights Infrastructure: Completion of Digital Foundation and Enabling Capability Design | 2028-07-01 | 2029-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
I.c.3 | Knowledge and Insights Infrastructure: Demonstration that the Digital Foundation supports measurable transformation | 2028-07-01 | 2029-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Demonstrate that shared capabilities and the Digital Foundation enable measurable transformation through priority use cases | 2028-07-01 | 2029-07-31 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Identification of long-term funding streams | 2028-01-01 | 2030-07-30 | Not Yet Started | Allison Adams
| Complete Initial CCi Program Evaluation | 2028-01-01 | 2028-09-30 | Not Yet Started | Allison Adams, Dr. Sarah Lewis
Checkpoint 4.1 Share final deliverables plan with CMS
|  | 2028-07-01 | 2029-03-31 | Not Yet Started | Andrea Adams
Checkpoint 4.2 CMS approval of final deliverables plan
|  | 2029-04-01 | 2029-04-30 | Not Yet Started | CMS
Checkpoint 4.3 Complete post-program planning
|  | 2029-05-01 | 2030-06-30 | Not Yet Started | Leadership Team
Stage 5 | Fully Implemented
I.a | RCH Hubs statewide in all 15 ADDs | 2030-10-01 | 2030-10-30 | Not Yet Started | Allison Adams
I.c.1 | Vitality Signs: Continue adding and refining data, measures, and functionality | 2029-08-01 | 2030-09-30 | Not Yet Started | Dr. Sarah Lewis
I.c.1 | Vitality Signs - RCH Partner Collaboration Workspace Enhancement in collaboration with RCH | 2029-10-01 | 2030-09-30 | Not Yet Started | Dr. Sarah Lewis, Allison Adams
| Contingent on "build, buy, or do without" decision, RCH Partner Collaboration Workspace (version 1) in all 15 ADDs | 2029-10-01 | 2030-09-30 | Not Yet Started | Dr. Sarah Lewis, Allison Adams
I.c.2 | Community Care Coordination: Expand clinical and community workflows | 2029-08-01 | 2030-09-30 | Not Yet Started | Tom Walton
I.c.3 | Knowledge and Insights Infrastructure: Connect at least one additional system using national standards (4 total connections) | 2029-08-01 | 2030-09-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
I.c.3 | Knowledge and Insights Infrastructure/LHS: Mature governance, continuous learning, evaluation, and sustainable operating model | 2029-08-01 | 2030-09-30 | Not Yet Started | Tom Walton, Dr. John Langefeld
| Long-term funding streams secured | 2030-07-01 | 2030-10-30 | Not Yet Started | Allison Adams
| RCH program transferred to non-profit, university, or PPP for sustainability | 2030-07-01 | 2030-10-30 | Not Yet Started | Allison Adams
| Complete Final CCi Program Evaluation | 2030-07-01 | 2030-12-15 | Not Yet Started | Allison Adams, Dr. Sarah Lewis
Checkpoint 5.1 Submit final deliverables to CMS
I | Final deliverables completed and submitted to CMS | 2030-07-01 | 2031-02-27 | Not Yet Started | Andrea Adams
Checkpoint 5.2 Complete all 2030 milestones
I | All CCi 2030 milestones are complete | 2030-07-01 | 2030-07-31 | Not Yet Started | Allison Adams
Checkpoint 5.3 Report updated metric progress to CMS
I | Updated metric progress report sumitted to CMS | 2030-10-30 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Allison Adams
| Submit Final Report to CMS | 2030-10-30 | 2031-02-27 | Not Yet Started | Andrea Adams

## II. PoWER Project Plan
| Initiative II: PoWERing Maternal and Infant Health | Key |  | Status Report
|  | Stage | 48 | Complete
| Designated State Lead: Dr. Alisha Morgan, Dr. Connie White (Interim) | Milestone | 15 | In Progress - On Track
|  | Task | 1 | In Progress - Behind Schedule
|  |  | 39 | Not Yet Started
|  |  | 0 | Upcoming
Milestones in red font have been completed
Checkpoints highlighted in yellow have been met
Stage | Milestones/Tasks | Target Start | Target Due Date | Status Report | Task Owner | Notes
Component |  |  |  | as of 7/31/2026 |  | Documentation is provided in the Checkpoint Evidence Attachment (CEA)
Stage 0 | Planning
II | Stand up PoWER Team | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Select staffing mechansim(s) | 2026-01-01 | 2026-02-01 | Complete | Dr. John Langefeld, Andrew Yunt
| Establish CHFS internal advisors for PoWER | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Kickoff Meeting with A3 leadership team, key partners, and support team (all initiatives) | 2026-01-06 | 2026-01-06 | Complete | Dr. John Langefeld, Tom Walton
| ADD selection criteria discussion (all initiatives) | 2026-02-19 | 2026-02-19 | Complete | Dr. Brent Wright, Andrea Adams
| PoWER stakeholder engagement strategy meeting (internal) | 2026-01-30 | 2026-01-30 | Complete | Dr. Connie White
| PoWER stakeholder engagement planning meeting (internal) | 2026-02-01 | 2026-02-01 | Complete | Dr. Connie White
| Checkpoint 0.1 Establish Governance |  |  |  |  | See Initiative Organization Chart, Role Descriptions and Staff Bios in CEA
II | Establish Governance | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Define initiative team operating model and governance structure | 2026-01-01 | 2026-01-27 | Complete | Dr. John Langefeld, Tom Walton
| Establish approval processes and operational decision flows for initiative design, budget, and execution | 2026-02-10 | 2026-05-20 | Complete | Dr. John Langefeld, Tom Walton
| Establish regular cadence for RHT financial reporting | 2026-02-09 | 2026-05-31 | Complete | Dr. John Langefeld, Tom Walton
| Procure and launch PM tool for initiative tracking and collaboration | 2026-04-02 | 2026-07-30 | Complete | Dr. John Langefeld, Tom Walton
| Compliance sprint to inform the development of the RHT subrecipient risk assessments process and monitoring plan | 2026-06-02 | 2026-06-30 | Complete | Dr. John Langefeld, Tom Walton
Checkpoint 0.2 Submit project plan to CMS
II | Develop Project Plan |  |  | In Progress - Behind Schedule | All Leads | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Refine milestones and flesh out acitvities in project plan | 2026-01-01 | 2026-06-26 | Complete | All Leads
| Submit project plan to CMS for informal review | 2026-06-29 | 2026-07-15 | Complete | Andrea Adams | submitted 7/30/2026
| Dialogue with CMS re: project plan | 2026-08-07 | 2026-08-31 | In Progress - On Track | Leadership Team
| Revise project plan based on CMS feedback | 2026-08-07 | 2026-08-31 | In Progress - On Track | Andrea Adams, All Leads
| Submit revised project plan to CMS | 2026-08-18 | 2026-08-31 | In Progress - On Track | Andrea Adams
Stage 1 | Initial Launch (public announcement or at least one contract signed or sub-recipient selected)
Checkpoint 1.1 CMS approval of project plan
I | Receive approval of project plan from CMS | 2026-07-15 | 2026-07-31 | Not Yet Started | CMS | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Checkpoint 1.2 Launch initiative |  |  |  |  | See Stakeholder Engagement section of CEA
II | Launch Initiative II (PoWER): Engage Stakeholders and/or Establish Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Executive Team, Drs. White and Morgan | Checkpoint 2.2 Achieve at least one post-launch milestone
| Press Release re: Kentucky RHT funding | 2025-12-29 | 2025-12-29 | Complete | Governor's Office | kentucky.gov/Pages/Activity-stream.aspx?n=GovernorBeshear&prId=2666
| KyRHT appearances before the Kentucky Legislature during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Project Sponsor and RHT Director testify before the Senate Standing Committee on Health Services | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| RHT Director testifies before the Interim Joint Budget Review Subcommittee of Health and Family Services Committee | 2026-06-03 | 2026-06-03 | Complete | Tom Walton
| RHT Director testifies before the Interim Joint Committee on Health Services | 2026-06-16 | 2026-06-16 | Complete | Tom Walton
| Develop "Jane's Journey" for PoWER Initiative | 2026-02-20 | 2026-03-30 | Complete | Jessi Watts, Dr. White and Team
| Develop 1-page PoWER handout for stakeholder meetings and conferences | 2026-04-01 | 2026-05-15 | Complete | Jessi Watts, Dr. Connie White | Included in CEA
| Stakeholder Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Dr. Connie White, Dr. Alisha Morgan | Details provided with Checkpoint Evidence
| Stakeholder Engagement during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Jessi Watts, Drs. White and Morgan | Details provided with Checkpoint Evidence
Stage 2 | Early Scale
| Checkpoint 2.1 Continue initiaitve activities (implementation) |  |  |  |  | Please consider this project plan as evidence for conitinued activites after PoWER Initiaitve Launch
II.b | Select Phase 1 pilot sites for PoWER Teams in 2 ADDs | 2026-06-01 | 2027-02-01 | Complete | Dr. Alisha Morgan | Checkpoint 2.2 Achieve at least one post-launch milestone
| Validate pilot prioritization approach | 2026-01-05 | 2026-06-15 | Complete | Dr. Connie White, Dr. Alisha Morgan
| Select initial pilot sites | 2026-05-01 | 2026-06-18 | Complete | Dr. Connie White, Dr. Alisha Morgan | Mountain Comprehensive Health Corp (Letcher & Harlan Counties); Baptist Deaconess Madisonsville
| Meetings to discuss contracts | 2026-06-18 | 2026-06-18 | Complete | Dr. Alisha Morgan | Contracts in final stages of review and aproval process
II.b | Create PoWER Team Implementation and Operations Guidance including participant eligibility | 2026-05-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
| Develop version 1 of guidance materials for PoWER team implementation and operations | 2026-05-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
| Develop eligibility criteria for participant inclusion in PoWER teams | 2026-05-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
| Finalize criteria for PoWER team participation eligibility | 2026-05-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
| Finalize Draft PoWER Operations Playbook for pilot phase | 2026-06-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
II.b | Enroll first patients at PoWER sites | 2026-08-01 | 2026-09-30 | Not Yet Started | Dr. Alisha Morgan
| Announce PoWER pilots and site locations in service areas of pilots | 2026-08-01 | 2026-09-30 | Not Yet Started | Dr. Alisha Morgan
| PoWER participant intake begins at Phase 1 pilot sites | 2026-10-01 | 2027-02-01 | Not Yet Started | Dr. Alisha Morgan
| Launch Phase 2 pilot sites to expand PoWER into 5 total ADDs | 2026-10-01 | 2027-10-01 | Not Yet Started | Dr. Alisha Morgan | "launch" = signed contract
II.b.1 | Develop eROP and ePRAF | 2026-01-05 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
| Develop draft eROP and ePRAF | 2026-01-05 | 2026-07-31 | Complete | Dr. Alisha Morgan
| Review of draft eROP and ePRAF by PoWER Advisory Sub-Workgroup | 2026-06-01 | 2026-06-15 | Complete | Dr. Connie White
| Finalize eROP and ePRAF | 2026-05-01 | 2026-09-30 | In Progress - On Track | Dr. Alisha Morgan
II.c.1 | Train PoWER Teams and Community Partners on Care Model | 2026-08-01 | 2027-07-31 | Not Yet Started | Dr. Alisha Morgan
II.c.2 | Select partner for co-developing a doula workforce expansion and strengthening strategy | 2026-05-01 | 2026-07-31 | Complete | Dr. Alisha Morgan | Checkpoint 2.2 Achieve at least one post-launch milestone
| Evaluate organizations for experience in doula education and capacity tobuild and sustain doula program | 2026-05-01 | 2026-07-31 | Complete | Dr. Alisha Morgan
| Select partner organization | 2026-07-31 | 2026-07-31 | Complete | Dr. Alisha Morgan | Contract signed on 7/31 with Kentucky Perinatal Quality Collaborative
II.c.2 | Develop a doula workforce expansion and strengthening strategy | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Alisha Morgan
| Facilitate development of a statewide doula workforce expansion and strengthening strategy | 2026-08-01 | 2027-09-30 | Not Yet Started | Dr. Alisha Morgan
II.c.3 | Develop Frontline Worker Training on Maternity and Infant Care | 2027-08-01 | 2028-06-30 | Not Yet Started | Dr. Alisha Morgan
II.c.4 | Establish Perinatal CHW certificate program | 2026-04-24 | 2027-06-30 | In Progress - On Track | Ashley Gibson
| Confirm PoWER program requirements for CHW capabilities | 2026-04-24 | 2026-05-15 | Complete | Ashley Gibson
| Finalize RFA scope and timeline | 2026-05-15 | 2026-06-19 | Complete | Ashley Gibson
| Release RFA for perinatal CHW specialized certificate training | 2026-07-15 | 2026-07-15 | Complete | Ashley Gibson
| Facilitate information session and office hours for potential partners | 2026-07-16 | 2026-07-24 | Complete | Ashley Gibson
| Finalize CHW specialized certificate training partners | 2026-08-05 | 2026-08-05 | Not Yet Started | Ashley Gibson
| Obtain approval for perinatal CHW specialized certificate training from KOCHW | 2027-06-30 | 2027-06-30 | Not Yet Started | Ashley Gibson
II.c.5 | Select regions for first wave HANDS expansion | 2026-06-01 | 2026-07-31 | Complete | Dr. Alisha Morgan | Checkpoint 2.2 Achieve at least one post-launch milestone
| Meet with state HANDS team to discuss expansion plan | 2026-06-01 | 2026-06-30 | Complete | Dr. Alisha Morgan
| Develop methodology for expansion and budget allocations by county and health department district | 2026-06-01 | 2026-07-31 | Complete | Dr. Alisha Morgan
| Select pilot regions | 2026-07-08 | 2026-07-08 | Complete | Dr. Alisha Morgan | based on HANDS utilzation data from 2021-2025
| Meet with local health department leadership in pilot regions | 2026-06-01 | 2026-07-31 | Complete | Dr. Alisha Morgan
| LHDs notified of selection via Teams call | 2026-07-29 | 2026-07-29 | Complete | Dr. Alisha Morgan | 3 district health departments and 5 independent LHDs selected (covering 19 rural counties)
| Award letters sent out | 2026-07-31 | 2026-07-31 | Complete | Dr. Alisha Morgan
II.c.5 | Formalize partnerships with LHDs in HANDS pilot regions and develop model for partnerships in future pilot regions | 2026-06-01 | 2027-02-01 | In Progress - On Track | Dr. Alisha Morgan
| Engage LHD leadership to define partnership scope within each pilot region | 2026-06-01 | 2026-07-03 | Complete | Dr. Alisha Morgan
| Negotiate and execute formal partnership agreement with pilot-region LHDs | 2026-07-01 | 2026-07-31 | In Progress - On Track | Dr. Alisha Morgan
| Develop a replicable LHD partnership model, including governance structure, engagement playbook, and standardized agreement templates | 2026-08-01 | 2027-02-01 | Not Yet Started | Dr. Alisha Morgan
II.c.5 | Adapt HANDS expansion plan to Phase 2 pilot site catchment areas | 2026-10-01 | 2027-10-01 | Not Yet Started | Dr. Alisha Morgan
II.c.6 | Select Health Care Workforce Pipeline Partners | 2026-01-01 | 2026-07-31 | Complete | Ashley Gibson | Checkpoint 2.2 Achieve at least one post-launch milestone
| Select organization(s) to support workforce pipeline in rural areas focusing on KyRHT related positions | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | UK contract started 7/1/2026; UofL contract starts 8/1/2026
II.c.6 | Implement a structured Maternal and Infant Health Career Pathway Program for high school and college students | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Dr. Alisha Morgan
| Provide career exploration, mentorship, and experiential learning opportunities including for potential Doulas and CHWs | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Dr. Alisha Morgan
Checkpoint 2.3 Establish Reporting Methodology
| Submit Metric Reporting Methodology Report to CMS | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
| Develop finalized metric approaches including how methodologies are being implemented in practice | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
Checkpoint 2.4 Submit updated project plan to CMS
| Updated Project Plan sent to CMS | 2026-11-01 | 2028-05-30 | Not Yet Started | Andrea Adams
Stage 3 | Implementation Mid-point 2Q28
Checkpoint 3.1 Receive CMS approval of updated project plan
| Updated Project Plan Approved by CMS | 2028-06-01 | 2028-06-30 | Not Yet Started | CMS
Checkpoint 3.2 Complete 2Q28 milestones
II.b | Launch Phase 3 pilot sites to expand PoWER into 10 total ADDs | 2027-10-01 | 2028-10-01 | Not Yet Started | Dr. Alisha Morgan | "launch" = signed contract
II.c.5 | Develop model for community education program with LHDs | 2027-01-01 | 2028-06-30 | Not Yet Started | Dr. Alisha Morgan
II.c.5 | Adapt HANDS expansion plan to Phase 3 pilot site catchment areas | 2027-10-01 | 2028-10-01 | Not Yet Started | Dr. Alisha Morgan
| Complete preliminary program evaluation | 2028-03-01 | 2028-09-30 | Not Yet Started | Dr. Alisha Morgan
Checkpoint 3.3 Report initial metric progress to CMS
| Initial Metric Progress and/or Reporting Methods Report sent to CMS | 2028-07-01 | 2028-12-30 | Not Yet Started | Dr. Sarah Lewis
Stage 4 | Near Completion
II.b | Launch Phase 4 pilot sites to expand PoWER into all 15 ADDs | 2028-10-01 | 2029-10-01 | Not Yet Started | Dr. Alisha Morgan | "launch" = signed contract
II.c.5 | Adapt HANDS expansion plan to Phase 4 pilot site catchment areas | 2028-10-01 | 2029-10-01 | Not Yet Started | Dr. Alisha Morgan
| Develop PoWER Team billing options with Medicaid | 2029-10-01 | 2030-09-30 | Not Yet Started | Dr. Alisha Morgan
| Explore PoWER Team billing options with 10 largest private insurers in KY | 2029-10-01 | 2030-09-30 | Not Yet Started | Dr. Alisha Morgan
| Explore alternative payment model (APM) opportunities to promote long-term sustainability | 2028-10-01 | 2029-09-30 | Not Yet Started | Dr. Alisha Morgan
| Complete Initial PoWER Program Evaluation | 2028-01-01 | 2028-09-30 | Not Yet Started | Dr. Sarah Lewis, Dr. Alisha Morgan
Checkpoint 4.1 Share final deliverables plan with CMS
|  | 2028-07-01 | 2029-03-31 | Not Yet Started | Andrea Adams
Checkpoint 4.2 CMS approval of final deliverables plan
|  | 2029-04-01 | 2029-04-30 | Not Yet Started | CMS
Checkpoint 4.3 Complete post-program planning
|  | 2029-05-01 | 2030-06-30 | Not Yet Started | Leadership Team
Stage 5 | Fully Implemented
II.b | Develop guide to support statewide independent site-driven implementation of the PoWER model | 2029-10-01 | 2030-12-31 | Not Yet Started | Dr. Alisha Morgan
| Secure sustainable funding (e.g., POWER Teams reimbursable through MCOs and private payers) | 2030-10-01 | 2031-09-30 | Not Yet Started | Dr. Alisha Morgan
| Complete Final PoWER Program Evaluation | 2030-07-01 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Dr. Alisha Morgan
Checkpoint 5.1 Submit final deliverables to CMS
II | Final deliverables completed and submitted to CMS | 2030-07-01 | 2031-02-27 | Not Yet Started | Andrea Adams
Checkpoint 5.2 Complete all 2030 milestones
II | All PoWER 2030 milestones are complete | 2030-07-01 | 2030-07-31 | Not Yet Started | Dr. Alisha Morgan
Checkpoint 5.3 Report updated metric progress to CMS
II | Updated metric progress report sumitted to CMS | 2030-10-30 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Dr. Alisha Morgan
| Submit Final Report to CMS | 2030-10-30 | 2031-02-27 | Not Yet Started | Andrea Adams

## III. RRR Project Plan
| Initiative III: Rapid Response to Recovery: EmPATH Model, Crisis Response, and Telebehavioral Health Hub (R3) | Key |  | Status Report
|  | Stage | 57 | Complete
| Designated State Lead: Breanna McGinnis | Milestone | 16 | In Progress - On Track
|  | Task | 1 | In Progress - Behind Schedule
|  |  | 56 | Not Yet Started
|  |  | 0 | Upcoming
Milestones in red font have been completed
Checkpoints highlighted in yellow have been met
Stage |  | Target Start | Target Due Date | Status Report | Task Owner | Notes
Component |  |  |  | as of 7/31/2026 |  | Documentation is provided in the Checkpoint Evidence Attachment (CEA)
Stage 0 | Planning
III | Stand up RRR Team | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Select staffing mechansim(s) | 2026-01-01 | 2026-02-01 | Complete | Dr. John Langefeld, Andrew Yunt
| Establish CHFS internal advisors for R3 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Kickoff Meeting with A3 leadership team, key partners, and support team (all initiatives) | 2026-01-06 | 2026-01-06 | Complete | Dr. John Langefeld, Tom Walton
| ADD selection criteria discussion (all initiatives) | 2026-02-19 | 2026-02-19 | Complete | Dr. Brent Wright, Andrea Adams
| R3 stakeholder engagement planning meeting (internal) | 2026-01-29 | 2026-01-29 | Complete | Breanna McGinnis, Andrew Bledsoe
| Checkpoint 0.1 Establish Governance |  |  |  |  | See Initiative Organization Chart, Role Descriptions and Staff Bios in CEA
III | Establish Governance | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Define initiative team operating model and governance structure | 2026-01-01 | 2026-01-27 | Complete | Dr. John Langefeld, Tom Walton
| Establish approval processes and operational decision flows for initiative design, budget, and execution | 2026-02-10 | 2026-05-20 | Complete | Dr. John Langefeld, Tom Walton
| Establish regular cadence for RHT financial reporting | 2026-02-09 | 2026-05-31 | Complete | Dr. John Langefeld, Tom Walton
| Procure and launch PM tool for initiative tracking and collaboration | 2026-04-02 | 2026-07-30 | Complete | Dr. John Langefeld, Tom Walton
| Compliance sprint to inform the development of the RHT subrecipient risk assessments process and monitoring plan | 2026-06-02 | 2026-06-30 | Complete | Dr. John Langefeld, Tom Walton
Checkpoint 0.2 Submit project plan to CMS
I | Develop Project Plan |  |  | In Progress - Behind Schedule | All Leads | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Refine milestones and flesh out acitvities in project plan | 2026-01-01 | 2026-06-26 | Complete | All Leads
| Submit project plan to CMS for informal review | 2026-06-29 | 2026-07-15 | Complete | Andrea Adams | submitted 7/30/2026
| Dialogue with CMS re: project plan | 2026-08-07 | 2026-08-31 | In Progress - On Track | Leadership Team
| Revise project plan based on CMS feedback | 2026-08-07 | 2026-08-31 | In Progress - On Track | Andrea Adams, All Leads
| Submit revised project plan to CMS | 2026-08-18 | 2026-08-31 | In Progress - On Track | Andrea Adams
Stage 1 | Initial Launch (public announcement or at least one contract signed or sub-recipient selected)
Checkpoint 1.1 CMS approval of project plan
I | Receive approval of project plan from CMS | 2026-07-15 | 2026-07-31 | Not Yet Started | CMS | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Checkpoint 1.2 Launch initiative |  |  |  |  | See Stakeholder Engagement section of CEA
III | Launch Initiative III (R3): Engage Stakeholders and/or Estabish Advisory Groups | 2025-12-29 | 2026-07-31 | Complete | Breanna McGinnis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Press Release re: Kentucky RHT funding | 2025-12-29 | 2025-12-29 | Complete | Governor's Office | kentucky.gov/Pages/Activity-stream.aspx?n=GovernorBeshear&prId=2666
| KyRHT appearances before the Kentucky Legislature during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Project Sponsor and RHT Director testify before the Senate Standing Committee on Health Services | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| RHT Director testifies before the Interim Joint Budget Review Subcommittee of Health and Family Services Committee | 2026-06-03 | 2026-06-03 | Complete | Tom Walton
| RHT Director testifies before the Interim Joint Committee on Health Services | 2026-06-16 | 2026-06-16 | Complete | Tom Walton
| Develop "Jane's Journey" for R3 Initiative | 2026-02-20 | 2026-03-17 | Complete | Breanna McGinnis, Team
| Develop 1-page RRR handout for stakeholder meetings and conferences | 2026-04-01 | 2026-05-15 | Complete | Jessi Watts, Breanna McGinnis | Included in CEA
| Stakeholder Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Breanna McGinnis | Details provided with Checkpoint Evidence
| Stakeholder Engagement during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Jessi Watts, Breanna McGinnis | Details provided with Checkpoint Evidence
| Establish EmPATH Consortium stakeholder advisory group | 2026-04-06 | 2026-07-31 | Complete | Breanna McGinnis
| Re-engage with key partners | 2026-04-06 | 2026-05-01 | Complete | Breanna McGinnis
| Contract with organization to support the Consortium | 2026-07-01 | 2026-07-01 | Complete | Breanna McGinnis | UK contract to support Consortium start date was 7/1
| Meeting to finalize kickoff agenda | 2026-07-16 | 2026-07-16 | Complete | Breanna McGinnis
| First Consortium Meeting | 2026-07-30 | 2026-07-30 | Complete | Breanna McGinnis
| Organize and facilitate consortium working groups | 2026-07-30 | 2026-07-30 | Complete | Breanna McGinnis | Consortium subcommittee topics identified in MOA with UK
Stage 2 | Early Scale
| Checkpoint 2.1 Continue initiaitve activities (implementation) |  |  |  |  | Please consider this project plan as evidence for conitinued activites after R3 Initiaitve Launch
III.a | Select pilot EmPATH hospital(s) Eastern Kentucky | 2026-01-05 | 2026-06-12 | Complete | Breanna McGinnis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Initial work planning, team structure, and stakeholder engagement | 2026-01-05 | 2026-03-15 | Complete | Breanna McGinnis
| Meet with shortlist of pilot hospitals | 2026-02-16 | 2026-03-27 | Complete | Breanna McGinnis | UK King's Daughter is in the process of contracting (budget approved)
| Applicants submiited proposals | 2026-05-01 | 2026-05-01 | Complete | Breanna McGinnis | ARH waiting on CMS approval of renovation costs before signigng
| Select Year 1 EmPATH pilot site(s) | 2026-05-15 | 2026-05-15 | Complete | Breanna McGinnis | two hospitals applied; both selected; both are in the contracting process
III.a | Implement EmPATH pilots in Eastern Kentucky | 2026-04-06 | 2027-09-30 | In Progress - On Track | Breanna McGinnis
| Facilitate implementation planning with Y1 pilot(s) | 2026-04-06 | 2026-06-12 | Complete | Breanna McGinnis
| Onboard partner to EmPATH pilot sites in Eastern Kentucky | 2026-10-01 | 2026-10-31 | Not Yet Started | Breanna McGinnis (UK)
| Develop pilot workflows and protocols | 2026-10-01 | 2027-03-31 | Not Yet Started | Breanna McGinnis (ARH, KD)
| Train pilot site staff | 2026-11-01 | 2027-07-31 | Not Yet Started | Breanna McGinnis (ARH, KD)
| Design and implement data collection methodology for outcomes assessment | 2026-10-01 | 2027-07-31 | Not Yet Started | Breanna McGinnis (ARH, KD)
| Monitor pilot performance and outcomes | 2026-11-01 | 2027-09-30 | Not Yet Started | Breanna McGinnis (ARH, KD)
III.b.1 | Determine telebehavioral health readiness, determine delivery model, & select support services partner(s) | 2026-03-02 | 2026-07-24 | Complete | Breanna McGinnis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Launch CMHC telebehavioral health landscape survey | 2026-03-02 | 2026-03-27 | Complete | Breanna McGinnis
| Conduct voice of the customer interviews | 2026-03-02 | 2026-04-10 | Complete | Breanna McGinnis
| Facilitate Collaborative Care Model (WA) validation workshop | 2026-04-06 | 2026-05-01 | Complete | Breanna McGinnis
| Conduct Payer, Medicaid, and compliance alignment | 2026-05-04 | 2026-05-29 | Complete | Breanna McGinnis
| Complete telebehavioral health hub readiness assessment for CMHCs and primary care providers (PCPs) | 2026-05-29 | 2026-05-29 | Complete | Breanna McGinnis | KPCA, UK, and UofL will serve centralized hub functions
| Release Telebehavioral Health Support Services RFA (BH clinical services) | 2026-06-01 | 2026-06-01 | Complete | Breanna McGinnis
| Application deadline | 2026-07-03 | 2026-07-03 | Complete | Breanna McGinnis | 11 applied; 4 selected to serve as regional "spokes" (BH clinical service providers)
| Telebehavioral Health Support Services selected | 2026-07-07 | 2026-07-07 | Complete | Breanna McGinnis | contracts in final stages of approval
III.b.1 | Build telebehavioral health hub central infrastructure and a regional spoke in at least 1 ADD region | 2026-10-01 | 2027-09-30 | In Progress - On Track | Breanna McGinnis
| Define hub-and-spoke operating model, service scope, and clinical workflows | 2026-07-01 | 2026-08-01 | In Progress - On Track | Breanna McGinnis | Centralized infrastructure between UK and UofL, Regional Provider Spokes
| Finalize technology platform intergrations and data interoperability standards for central infrastructure | 2026-07-01 | 2027-04-01 | In Progress - On Track | Tech Partners
| Build and pilot technology central infrastructure | 2026-07-01 | 2027-04-01 | In Progress - On Track | Tech Partners
| Develop hub-and-spoke governance and workflows | 2026-09-01 | 2027-12-01 | Not Yet Started | Breanna McGinnis (UK, UofL) | Deliverable of UK+UofL
| Launch hub-and-spoke operations with selected PCPs | 2027-04-01 | 2027-09-30 | Not Yet Started | Breanna McGinnis (UK, UofL, Spoke BH Providers, PCPs)
III.b.1 | Award at least 5 primary care providers to participate in the telebehavioral hub | 2026-12-01 | 2027-04-01 | In Progress - On Track | Breanna McGinnis
| Draft participation opportunity materials, including post-release materials (announcement, info session, and office hours) | 2026-12-01 | 2026-12-31 | Not Yet Started | Breanna McGinnis (KPCA)
| Solicit provider applications from PCPs in pilot ADDs | 2026-12-01 | 2027-01-31 | Not Yet Started | Breanna McGinnis (KPCA)
| Facilitate information session and office hours for PCPs | 2026-12-15 | 2027-01-31 | Not Yet Started | Breanna McGinnis (KPCA)
| Send Notice of Awards (NOA) to selected PCPs | 2027-01-15 | 2027-01-31 | Not Yet Started | Breanna McGinnis (KPCA)
| Finalize contracting with selected PCPs | 2027-02-01 | 2027-04-01 | Not Yet Started | Breanna McGinnis (KPCA)
| Finalize training and technical assistance deliverables | 2026-10-01 | 2027-04-01 | Not Yet Started | Breanna McGinnis (KPCA)
III.b.2 | Select 988 Crisis Response Technology | 2026-01-01 | 2026-07-31 | Complete | Breanna McGinnis | Checkpoint 2.2 Achieve at least one post-launch milestone
| 988 - RHT data discussion | 2026-02-12 | 2026-02-12 | Complete | Breanna McGinnis
| Vendor cleared CHFS technology security review | 2026-06-01 | 2026-06-11 | Complete | A3 Tech Operations Team
| Technology partner notified of selection | 2026-06-23 | 2026-06-23 | Complete | Breanna McGinnis | Contract is in final stages of approval process
III.c | Select CMHCs to Support EmPATH Units and/or Community-Based Crisis Support Programs | 2026-03-02 | 2026-07-24 | Complete | Breanna McGinnis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Develop RFA plan | 2026-03-02 | 2026-04-16 | Complete | Breanna McGinnis
| Release CMHC Support RFA | 2026-06-01 | 2026-06-01 | Complete | Breanna McGinnis | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| Facilitate RFA prioritization working group | 2026-06-12 | 2026-06-30 | Complete | Breanna McGinnis
| Application Deadline (extended to 7/6) | 2026-07-03 | 2026-07-03 | Complete | Breanna McGinnis | 9 applied 8 selected (KY has 15 CMHC regions): 5 for CBCS only and 3 for both CBCS and EmPATH
| CMHCs selected | 2026-07-24 | 2026-07-24 | Complete | Breanna McGinnis | Contracts are in final stages of approval process - awaiting signatures
III.d | Select CMHCs to Pilot 202a and Crisis Transportation Intervention Strategies | 2026-06-01 | 2027-07-31 | In Progress - On Track | Breanna McGinnis (DBHDID)
| In collaboration with DBHDID and CHFS OAS, determine contracting pathway | 2026-06-01 | 2026-08-21 | In Progress - On Track | Breanna McGinnis (DBHDID)
| Select CMHCs | 2026-09-16 | 2027-05-31 | Not Yet Started | Breanna McGinnis (DBHDID)
III.e.1 | First Responder Training, TA, and Relationship Building | 2026-10-01 | 2027-09-30 | In Progress - On Track | Breanna McGinnis | Regional CMHCs to provide training, TA, partnership with EMS
| Onboard community paramedicine/EMS agency partners across 5 target counties | 2026-10-01 | 2026-12-01 | Not Yet Started | Breanna McGinnis (CMHCs)
| Develop behavioral health crisis training curriculum and technical assistance framework | 2026-10-01 | 2026-12-01 | Not Yet Started | Breanna McGinnis (CMHCs)
| Establish data collection protocols, tools, and reporting cadence | 2026-10-01 | 2026-12-15 | Not Yet Started | Breanna McGinnis (CMHCs)
| Compile and analyze initial engagement data | 2026-12-07 | 2027-04-20 | Not Yet Started | Breanna McGinnis (CMCHs)
| Pilot 202a and voluntary crisis transportation model by obligating funding to pilot partner site | 2026-10-30 | 2027-09-30 | In Progress - On Track | Breanna McGinnis (CMCHs)
| Begin phased implementation roll out of BHL technology across atleast 4 CMHCs | 2026-10-01 | 2026-12-31 | In Progress - On Track | Breanna McGinnis (BHL)
III.e.2 | Select Health Care Workforce Pipeline Partners | 2026-01-01 | 2026-07-31 | Complete | Ashley Gibson | Checkpoint 2.2 Achieve at least one post-launch milestone
| Select organization(s) to support workforce pipeline in rural areas focusing on KyRHT related positions | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | UK contract started 7/1/2026; UofL contract starts 8/1/2026
III.e.2 | Stigma Reduction Training Focused on SUD for First Responders | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Breanna McGinnis
| Provide Stigma Reduction Training Focused on SUD for at least 20 First Responders | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Breanna McGinnis
Checkpoint 2.3 Establish Reporting Methodology
| Submit Metric Reporting Methodology Report to CMS | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
| Develop finalized metric approaches including how methodologies are being implemented in practice | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
Checkpoint 2.4 Submit updated project plan to CMS
| Updated Project Plan sent to CMS | 2026-11-01 | 2028-05-30 | Not Yet Started | Andrea Adams
Stage 3 | Implementation Mid-point 2Q28
Checkpoint 3.1 Receive CMS approval of updated project plan
| Updated Project Plan Approved by CMS | 2028-06-01 | 2028-06-30 | Not Yet Started | CMS
Checkpoint 3.2 Complete 2Q28 milestones
III.a | Expand the EmPATH model to at least one new ADD | 2026-10-01 | 2028-06-30 | Not Yet Started | Breanna McGinnis | UK to provide TA
III.b | Expand telebehavioral health hub to support at least 10 users (i.e. rural EDs, PCPs, and first responders) in one ADD region | 2027-03-01 | 2029-01-01 | Not Yet Started | Breanna McGinnis
| Publish RFA for regional provider spokes in new region of state | 2027-03-01 | 2027-04-01 | Not Yet Started | Breanna McGinnis
| Select PCPs in new region | 2027-04-01 | 2027-07-01 | Not Yet Started | Breanna McGinnis
| Launch contracts with new behavioral health regional provider spokes, executed MOA | 2027-07-01 | 2029-01-01 | Not Yet Started | Breanna McGinnis
| Onboard new users into the telebehavioral health hub | 2027-07-01 | 2029-01-01 | Not Yet Started | Breanna McGinnis
III.c.1 | Expand CMHC Support to new EmPATH site(s) | 2027-07-01 | 2028-06-30 | Not Yet Started | Breanna McGinnis
III.c.2 | Expand CMHC Support to Community-Based Crisis Support Programs to at least 5 new counties | 2027-07-01 | 2028-12-31 | Not Yet Started | Breanna McGinnis
| RFA for CMHC Support to EmPATH, Paramedicine , and CBCS Programs to CMHCs not selected/did not apply in BP1 | 2027-03-01 | 2027-04-01 | Not Yet Started | Breanna McGinnis
| New CMHC onboarding and services begin through executed MOA | 2027-07-01 | 2028-12-31 | Not Yet Started | Breanna McGinnis
| Request continuation applications from existing awarded CMHCs, extension begins | 2027-10-01 | 2028-12-31 | Not Yet Started | Breanna McGinnis
| Match at least 5 new first responder agencies (from CTC awardees or new partners outside of RHT) to CMHCs | 2027-10-01 | 2028-12-31 | Not Yet Started | Breanna McGinnis
III.d | 202a and Crisis Transportation Pilot Expansion | 2027-01-01 | 2028-06-30 | Not Yet Started | Breanna McGinnis (DBHDID)
Checkpoint 3.3 Report initial metric progress to CMS
| Initial Metric Progress and/or Reporting Methods Report sent to CMS | 2028-07-01 | 2028-12-30 | Not Yet Started | Dr. Sarah Lewis
Stage 4 | Near Completion
III.a | Expand the EmPATH model to at least one new ADD | 2029-01-01 | 2031-06-30 | Not Yet Started | Breanna McGinnis
III.b | Expand telebehavioral health hub to support at least 10 new users (i.e. rural EDs, PCPs, and first responders) in one additional ADD | 2028-07-01 | 2029-06-30 | Not Yet Started | Breanna McGinnis
III.c.1 | Expand CMHC Support to new EmPATH site(s) | 2028-07-01 | 2029-06-30 | Not Yet Started | Breanna McGinnis
III.c.2 | Expand CMHC Support Community-Based Crisis Support Programs to at least 5 new counties | 2028-07-01 | 2029-06-30 | Not Yet Started | Breanna McGinnis
| Complete Initial R3 Program Evaluation | 2028-01-01 | 2028-09-30 | Not Yet Started | Dr. Sarah Lewis, Breanna McGinnis
Checkpoint 4.1 Share final deliverables plan with CMS
|  | 2028-07-01 | 2029-03-31 | Not Yet Started | Andrea Adams
Checkpoint 4.2 CMS approval of final deliverables plan
|  | 2029-04-01 | 2029-04-30 | Not Yet Started | CMS
Checkpoint 4.3 Complete post-program planning
|  | 2029-05-01 | 2030-06-30 | Not Yet Started | Leadership Team
Stage 5 | Fully Implemented
III.a | Scale the existing EmPATH units to increase regional impact through teleservices, partnerships, and other tailored rural approaches | 2029-07-01 | 2030-06-30 | Not Yet Started | Breanna McGinnis
III.b | Expand telebehavioral health hub to support at least 20 new users (i.e. rural EDs, PCPs, and first responders) in 2 additional ADDs | 2029-07-01 | 2030-06-30 | Not Yet Started | Breanna McGinnis
III.c | Expand community-based crisis support program to up to 10 new counties | 2029-07-01 | 2031-06-30 | Not Yet Started | Breanna McGinnis
| Publish public KPI dashboard | 2029-07-01 | 2031-06-30 | Not Yet Started | Breanna McGinnis
| Publish leading practices, case studies, and learnings | 2031-07-01 | 2031-09-30 | Not Yet Started | Breanna McGinnis
| Complete Final R3 Program Evaluation | 2030-07-01 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Breanna McGinnis
Checkpoint 5.1 Submit final deliverables to CMS
III | Final deliverables completed and submitted to CMS | 2030-07-01 | 2031-02-27 | Not Yet Started | Andrea Adams
Checkpoint 5.2 Complete all 2030 milestones
III | All RRR 2030 milestones are complete | 2030-07-01 | 2030-07-31 | Not Yet Started | Breanna McGinnis
Checkpoint 5.3 Report updated metric progress to CMS
III | Updated metric progress report sumitted to CMS | 2030-10-30 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Breanna McGinnis
| Submit Final Report to CMS | 2030-10-30 | 2031-02-27 | Not Yet Started | Andrea Adams

## IV. RiH Project Plan
| Initiative IV: Rooted in Health: Rural Dental Access Program (RIH) | Key |  | Status Report
|  | Stage | 71 | Complete
| Designated State Lead: Dr. John Landis | Milestone | 10 | In Progress - On Track
|  | Task | 1 | In Progress - Behind Schedule
|  |  | 35 | Not Yet Started
|  |  | 0 | Upcoming
Milestones in red font have been completed
Checkpoints highlighted in yellow have been met
Stage | Milestones/Tasks | Target Start | Target Due Date | Status Report | Task Owner | Notes
Component |  |  |  | as of 7/31/2026 |  | Documentation is provided in the Checkpoint Evidence Attachment (CEA)
Stage 0 | Planning
IV | Stand up RiH Team | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Select staffing mechansim(s) | 2026-01-01 | 2026-02-01 | Complete | Dr. John Langefeld, Andrew Yunt
| Establish CHFS internal advisors for RiH | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Kickoff Meeting with A3 leadership team, key partners, and support team (all initiatives) | 2026-01-06 | 2026-01-06 | Complete | Dr. John Langefeld, Tom Walton
| ADD selection criteria discussion (all initiatives) | 2026-02-19 | 2026-02-19 | Complete | Dr. Brent Wright, Andrea Adams
| RiH stakeholder engagement planning meeting (internal) | 2026-01-29 | 2026-01-29 | Complete | Dr. Pam Stein, Andrew Bledsoe
| Checkpoint 0.1 Establish Governance |  |  |  |  | See Initiative Organization Chart, Role Descriptions and Staff Bios in CEA
IV | Establish Governance | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Define initiative team operating model and governance structure | 2026-01-01 | 2026-01-27 | Complete | Dr. John Langefeld, Tom Walton
| Establish approval processes and operational decision flows for initiative design, budget, and execution | 2026-02-10 | 2026-05-20 | Complete | Dr. John Langefeld, Tom Walton
| Establish regular cadence for RHT financial reporting | 2026-02-09 | 2026-05-31 | Complete | Dr. John Langefeld, Tom Walton
| Procure and launch PM tool for initiative tracking and collaboration | 2026-04-02 | 2026-07-30 | Complete | Dr. John Langefeld, Tom Walton
| Compliance sprint to inform the development of the RHT subrecipient risk assessments process and monitoring plan | 2026-06-02 | 2026-06-30 | Complete | Dr. John Langefeld, Tom Walton
Checkpoint 0.2 Submit project plan to CMS
IV | Develop Project Plan |  |  | In Progress - Behind Schedule | All Leads | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Refine milestones and flesh out acitvities in project plan | 2026-01-01 | 2026-06-26 | Complete | All Leads
| Submit project plan to CMS for informal review | 2026-06-29 | 2026-07-15 | Complete | Andrea Adams | submitted 7/30/2026
| Dialogue with CMS re: project plan | 2026-08-07 | 2026-08-31 | In Progress - On Track | Leadership Team
| Revise project plan based on CMS feedback | 2026-08-07 | 2026-08-31 | In Progress - On Track | Andrea Adams, All Leads
| Submit revised project plan to CMS | 2026-08-18 | 2026-08-31 | In Progress - On Track | Andrea Adams
Stage 1 | Initial Launch (public announcement or at least one contract signed or sub-recipient selected)
Checkpoint 1.1 CMS approval of project plan
I | Receive approval of project plan from CMS | 2026-07-15 | 2026-07-31 | Not Yet Started | CMS | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Checkpoint 1.2 Launch initiative |  |  |  |  | See Stakeholder Engagement section of CEA
IV | Launch Initiative IV (RiH): Engage Stakeholders and/or Establish Advisory Groups | 2025-12-29 | 2026-07-31 | Complete | Dr. Pam Stein, Dr. John Landis
| Press Release re: Kentucky RHT funding | 2025-12-29 | 2025-12-29 | Complete | Governor's Office | kentucky.gov/Pages/Activity-stream.aspx?n=GovernorBeshear&prId=2666
| KyRHT appearances before the Kentucky Legislature during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Project Sponsor and RHT Director testify before the Senate Standing Committee on Health Services | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| RHT Director testifies before the Interim Joint Budget Review Subcommittee of Health and Family Services Committee | 2026-06-03 | 2026-06-03 | Complete | Tom Walton
| RHT Director testifies before the Interim Joint Committee on Health Services | 2026-06-16 | 2026-06-16 | Complete | Tom Walton
| Develop "Jane's Journey" for Rooted in Health Initiative | 2026-02-20 | 2026-04-06 | Complete | Dr. Pam Stein, Dr. John Landis, Team
| Develop 1-page RiH handout for stakeholder meetings and conferences | 2026-04-01 | 2026-05-15 | Complete | Jessi Watts, Dr. John Landis | Included in CEA
| RiH Stakeholder Advisory Group Formed | 2026-05-09 | 2026-07-31 | Complete | Dr. John Landis | Details provided with Checkpoint Evidence
| RiH Stakeholder Engagement during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Jessi Watts, Drs. White and Morgan | Details provided with Checkpoint Evidence
Stage 2 | Early Scale
| Checkpoint 2.1 Continue initiaitve activities (implementation) |  |  |  |  | Please consider this project plan as evidence for conitinued activites after RiH Initiaitve Launch
IV.a.1 | Identify sites for new or expanded accredited dental hygiene programs​ | 2026-01-05 | 2026-07-31 | Complete | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Initial work planning, team structure, and stakeholder engagement | 2026-01-05 | 2026-03-15 | Complete | Dr. John Landis
| Engage with existing or new dental hygiene programs | 2026-02-05 | 2026-04-01 | Complete | Dr. John Landis
| Initiate contracting with select expansion-ready programs | 2026-03-04 | 2026-04-15 | Complete | Dr. John Landis
| Draft RFA and information session materials | 2026-03-04 | 2026-04-20 | Complete | Dr. John Landis
| Release accredited dental hygiene programs RFA | 2026-04-20 | 2026-04-20 | Complete | Dr. John Landis | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| Facilitate information session and office hours for potential partners | 2026-05-05 | 2026-05-29 | Complete | Dr. John Landis
| Application deadline | 2026-05-29 | 2026-05-29 | Complete | Dr. John Landis | Campbellsville University, Ky State University, UK-Hazard campus, and BCTCS selected
| Select funding recipients | 2026-07-23 | 2026-07-23 | Complete | Dr. John Landis | announcements pending contract approval; delayed awaiting CMS renovation approval
IV.a.2 | Identify expansion sites for Dental Assistant Training | 2026-05-01 | 2026-07-31 | Complete | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Identify partners for Dental Assistant training | 2026-05-01 | 2026-06-30 | Complete | Dr. John Landis | draft contracts and budgets in the queue for KPCA and KDA; expect signatues by 8/31/26
IV.a.3 | Contract with training partner(s) for advanced extraction training for rural dentists | 2026-04-08 | 2026-07-31 | Complete | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Facilitate scope alignment session | 2026-04-08 | 2026-04-08 | Complete | Dr. John Landis
| Refine scope and develop proposal guidance | 2026-04-08 | 2026-04-20 | Complete | Dr. John Landis
| Solicit proposals from training partner(s) | 2026-04-20 | 2026-05-08 | Complete | Dr. John Landis
| Select training partners | 2026-05-08 | 2026-05-08 | Complete | Dr. John Landis | KPCA and UK
| Work with training partner(s) to finalize SOWs and budgets | 2026-05-08 | 2026-08-15 | Complete | Dr. John Landis | UK contract signed; KPCA contract in progress
IV.a.6 | Select Health Care Workforce Pipeline Partners | 2026-01-01 | 2026-07-31 | Complete | Ashley Gibson | Checkpoint 2.2 Achieve at least one post-launch milestone
| Select organization(s) to support workforce pipeline in rural areas focusing on KyRHT related positions | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | UK contract started 7/1/2026; UofL contract starts 8/1/2026
IV.a.6 | Develop a Dental Hygiene School Preparation Program as part of Oral Health Career Pathway | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Dr. John Landis
| Design targeted support for high school and early college students to improve matriculation to Dental Hygiene programs | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Dr. John Landis
IV.a.6 | Establish statewide Peer-to-Pipeline Mentorship Program for Oral Health Careers | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson
| Design targeted support for high school and early college students to improve matriculation to oral health programs | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson
IV.b | Identify partners for teledental hubs​ | 2026-03-06 | 2026-08-15 | In Progress - On Track | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Initial re-engagement with teledental hub sites (x3) | 2026-03-06 | 2026-03-12 | Complete | Dr. John Landis | 3 Ky Dental Schools: UK, UofL, and UPike
| Develop teledental hub scope and proposal guidance | 2026-03-20 | 2026-04-08 | Complete | Dr. John Landis
| Conduct outreach and planning with teledental hub sites (x3) | 2026-03-20 | 2026-05-01 | Complete | Dr. John Landis
| Solicit proposals from teledental hub sites (x3) | 2026-05-01 | 2026-06-15 | Complete | Dr. John Landis
| Work with teledental hub sites (x3) to finalize SOWs and budgets | 2026-05-04 | 2026-07-24 | Complete | Dr. John Landis
| Submit SOW and budget documents for internal review | 2026-07-01 | 2026-07-31 | Complete | Dr. John Landis | UK contract signed; UofL and UPike contracts in progress
IV.b | Align 10 public health dental hygiene teams geographically to each dental college within the teledentistry pilot | 2026-09-01 | 2027-01-30 | In Progress - On Track | Dr. John Landis
| Research teledentistry leading practices | 2026-05-01 | 2026-08-10 | In Progress - On Track | Dr. John Landis
| Align with Board of Dentistry on teledentistry regulations | 2026-08-01 | 2027-06-01 | In Progress - On Track | Dr. John Landis
| Hold teledentistry leadership meeting to determine teledental hub service areas | 2026-08-13 | 2026-08-13 | Not Yet Started | Dr. John Landis
| Collaborate with universities to develop training and onboarding plan | 2026-09-01 | 2026-12-31 | Not Yet Started | Dr. John Landis
| Identify and onboard selected PHDH teams to teledental hubs | 2027-01-15 | 2027-02-15 | Not Yet Started | Dr. John Landis
| Launch and monitor initial pilot of teledental services for participating teams | 2027-02-28 | 2026-05-31 | Not Yet Started | Dr. John Landis
| Refine hub and spoke model to scale across additional PHDH teams | 2027-06-01 | 2027-09-30 | Not Yet Started | Dr. John Landis
IV.c.1 | Identify sites for new or expanded Public Health Dental Hygiene (PHDH) teams | 2026-01-26 | 2026-07-09 | Complete | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Determine procurement pathway | 2026-01-26 | 2026-02-02 | Complete | Dr. John Landis
| Draft RFA and information session materials | 2026-02-02 | 2026-03-20 | Complete | Dr. John Landis
| Conduct internal touchpoint on PHDH teams | 2026-02-16 | 2026-02-16 | Complete | Dr. John Landis
| Engage with select "early adopter" LHDs | 2026-02-16 | 2026-02-27 | Complete | Dr. John Landis
| Release RFA for New or Expanded PHDH Teams | 2026-03-20 | 2026-03-20 | Complete | Dr. John Landis | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| Facilitate information session and office hours for LHDs | 2026-03-20 | 2026-04-03 | Complete | Dr. John Landis
| Share RFA FAQs | 2026-04-08 | 2026-04-08 | Complete | Dr. John Landis
| Application deadline | 2026-04-24 | 2026-04-24 | Complete | Dr. John Landis
| Conduct RFA reviews to select LHDs | 2026-04-27 | 2026-05-29 | Complete | Dr. John Landis
| Finalize LHD selection, and draft award announcement | 2026-05-29 | 2026-06-17 | Complete | Dr. John Landis | 4 new teams: Bracken County, Greenup County, Ky River District, Pennyrile District
| Send notices of award to selected LHDs | 2026-06-17 | 2026-06-17 | Complete | Dr. John Landis
IV.c.2 | Identify PHDH teams to work on expanding scope to LTC | 2026-01-26 | 2026-07-09 | Complete | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Deadline for Local Health Departments with active Public Health Dental Hygiene teams to opt into scope expansion | 2026-04-24 | 2026-04-24 | Complete | Dr. John Landis | 100% of eligible LHDs (10) opted into scope expansion
| Send notices of award to selected LHDs | 2026-06-17 | 2026-06-17 | Complete | Dr. John Landis | In active contracting: finalizing budgets
IV.d.1 | Select funding recipients for definitive mobile dentistry services | 2026-04-15 | 2026-11-15 | In Progress - On Track | Dr. John Landis | Checkpoint 2.2 Achieve at least one post-launch milestone
| Confirm mobile dentistry program requirements | 2026-04-15 | 2026-04-30 | Complete | Dr. John Landis
| Finalize RFA scope and timeline | 2026-04-27 | 2026-05-10 | Complete | Dr. John Landis
| Release RFA for Definitive Mobile Dentistry Services | 2026-05-15 | 2026-05-15 | Complete | Dr. John Landis | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| RFA Information Session | 2026-05-21 | 2026-05-21 | Complete | Dr. John Landis
| Facilitate office hours for potential partners | 2026-05-29 | 2026-05-29 | Complete | Dr. John Landis
| Application deadline | 2026-06-12 | 6/12/206 | Complete | Dr. John Landis | 10 applied, 5 selected
| Finalize mobile dentistry partners | 2026-06-30 | 2026-09-01 | Complete | Dr. John Landis | Recipients selected 7/27/2026; in the process of finalizing contracts and budgets
IV.d.1 | Identify geographic service areas for definitive mobile dentistry service providers | 2026-08-03 | 2026-11-15 | Not Yet Started | Dr. John Landis
| Determine geographic service areas for initial pilot of mobile dentistry services | 2026-08-03 | 2026-11-15 | Not Yet Started | Dr. John Landis
Checkpoint 2.3 Establish Reporting Methodology
| Submit Metric Reporting Methodology Report to CMS | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
| Develop finalized metric approaches including how methodologies are being implemented in practice | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
Checkpoint 2.4 Submit updated project plan to CMS
| Updated Project Plan sent to CMS | 2026-11-01 | 2028-05-30 | Not Yet Started | Andrea Adams
Stage 3 | Implementation Mid-point 2Q28
Checkpoint 3.1 Receive CMS approval of updated project plan
| Updated Project Plan Approved by CMS | 2028-06-01 | 2028-06-30 | Not Yet Started | CMS
Checkpoint 3.2 Complete 2Q28 milestones
IV.a.1 | Graduate first students from new or expanded accredited dental hygiene programs | 2028-10-01 | 2028-06-01 | Not Yet Started | Dr. John Landis
Checkpoint 3.3 Report initial metric progress to CMS
| Initial Metric Progress and/or Reporting Methods Report sent to CMS | 2028-07-01 | 2028-12-30 | Not Yet Started | Dr. Sarah Lewis
Stage 4 | Near Completion
IV.c | Connect 50% of public health dental hygiene teams to a teledental hub, consulting dentist | 2027-03-30 | 2028-07-31 | Not Yet Started | Dr. John Landis
IV.d | Launch first mobile dentistry unit | 2028-10-01 | 2028-10-01 | Not Yet Started | Dr. John Landis
IV.a.3 | Provide at least one advanced extraction training in 4 ADDs | 2029-05-01 | 2029-07-31 | Not Yet Started | Dr. John Landis
| Display at least 5 oral health metrics in data dashboard | 2029-08-01 | 2030-09-30 | Not Yet Started | Dr. John Landis
| Complete Initial RiH Program Evaluation | 2028-01-01 | 2028-09-30 | Not Yet Started | Dr. Sarah Lewis, Dr. John Landis
Checkpoint 4.1 Share final deliverables plan with CMS
|  | 2028-07-01 | 2029-03-31 | Not Yet Started | Andrea Adams
Checkpoint 4.2 CMS approval of final deliverables plan
|  | 2029-04-01 | 2029-04-30 | Not Yet Started | CMS
Checkpoint 4.3 Complete post-program planning
|  | 2029-05-01 | 2030-06-30 | Not Yet Started | Leadership Team
Stage 5 | Fully Implemented
IV.a.1 | Increase the graduating dental hygiene class size by 50%, including programs in process of accreditation | 2030-10-01 | 2030-10-30 | Not Yet Started | Dr. John Landis
IV.a.2 | Provide didactic dental assistant training on a virtual learning platform for all 15 ADDs | 2031-07-01 | 2030-10-30 | Not Yet Started | Dr. John Landis
IV.a.3 | Provide access to at least one advanced extraction training within all 15 ADDs | 2031-04-01 | 2030-10-30 | Not Yet Started | Dr. John Landis
IV.c | Connect 75% of public health dental hygiene teams to a teledental hub, consulting dentist | 2029-10-01 | 2030-10-30 | Not Yet Started | Dr. John Landis
| Display at least 10 oral health metrics in data dashboard | 2030-10-01 | 2030-10-30 | Not Yet Started | Dr. John Landis
IV | Complete Final RiH Program Evaluation | 2030-07-01 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Dr. John Landis
Checkpoint 5.1 Submit final deliverables to CMS
IV | Final deliverables completed and submitted to CMS | 2030-07-01 | 2031-02-27 | Not Yet Started | Andrea Adams
Checkpoint 5.2 Complete all 2030 milestones
IV | All RiH 2030 milestones are complete | 2030-07-01 | 2030-07-31 | Not Yet Started | Dr. John Landis
Checkpoint 5.3 Report updated metric progress to CMS
IV | Updated metric progress report sumitted to CMS | 2030-10-30 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Dr. John Landis
| Submit Final Report to CMS | 2030-10-30 | 2031-02-27 | Not Yet Started | Andrea Adams

## V. CTC Project Plan
| Initiative V: From Crisis to Care: Integrated EMS and Trauma Response (CTC) | Key |  | Status Report
|  | Stage | 74 | Complete
| Designated State Lead: Joseph Riddle, Robbie Hume (Interim) | Milestone | 9 | In Progress - On Track
|  | Task | 1 | In Progress - Behind Schedule
|  |  | 59 | Not Yet Started
|  |  | 2 | Upcoming
Milestones in red font have been completed
Checkpoints highlighted in yellow have been met
Stage | Milestones/Tasks | Target Start | Target Due Date | Status Report | Task Owner | Notes
Component |  |  |  | as of 7/31/2026 |  | Documentation is provided in the Checkpoint Evidence Attachment (CEA)
Stage 0 | Planning
V | Stand up CTC Team | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Select staffing mechansim(s) | 2026-01-01 | 2026-02-01 | Complete | Dr. John Langefeld, Andrew Yunt
| Establish CHFS internal advisors for CTC | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Kickoff Meeting with A3 leadership team, key partners, and support team (all initiatives) | 2026-01-06 | 2026-01-06 | Complete | Dr. John Langefeld, Tom Walton
| ADD selection criteria discussion (all initiatives) | 2026-02-19 | 2026-02-19 | Complete | Dr. Brent Wright, Andrea Adams
| CTC stakeholder engagement planning meeting (internal) | 2026-02-28 | 2026-02-28 | Complete | Robbie Hume
| Checkpoint 0.1 Establish Governance |  |  |  |  | See Initiative Organization Chart, Role Descriptions and Staff Bios in CEA
V | Establish Governance | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Define initiative team operating model and governance structure | 2026-01-01 | 2026-01-27 | Complete | Dr. John Langefeld, Tom Walton
| Establish approval processes and operational decision flows for initiative design, budget, and execution | 2026-02-10 | 2026-05-20 | Complete | Dr. John Langefeld, Tom Walton
| Establish regular cadence for RHT financial reporting | 2026-02-09 | 2026-05-31 | Complete | Dr. John Langefeld, Tom Walton
| Procure and launch PM tool for initiative tracking and collaboration | 2026-04-02 | 2026-07-30 | Complete | Dr. John Langefeld, Tom Walton
| Compliance sprint to inform the development of the RHT subrecipient risk assessments process and monitoring plan | 2026-06-02 | 2026-06-30 | Complete | Dr. John Langefeld, Tom Walton
Checkpoint 0.2 Submit project plan to CMS
V | Develop Project Plan |  |  | In Progress - Behind Schedule | All Leads | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Refine milestones and flesh out acitvities in project plan | 2026-01-01 | 2026-06-26 | Complete | All Leads
| Submit project plan to CMS for informal review | 2026-06-29 | 2026-07-15 | Complete | Andrea Adams | submitted 7/30/2026
| Dialogue with CMS re: project plan | 2026-08-07 | 2026-08-31 | In Progress - On Track | Leadership Team
| Revise project plan based on CMS feedback | 2026-08-07 | 2026-08-31 | In Progress - On Track | Andrea Adams, All Leads
| Submit revised project plan to CMS | 2026-08-18 | 2026-08-31 | In Progress - On Track | Andrea Adams
Stage 1 | Initial Launch (public announcement or at least one contract signed or sub-recipient selected)
Checkpoint 1.1 CMS approval of project plan
I | Receive approval of project plan from CMS | 2026-07-15 | 2026-07-31 | Not Yet Started | CMS | Waiting on finalization of CMS guidance to open document submission process (received 8/14/2026)
| Checkpoint 1.2 Launch initiative |  |  |  |  | See Stakeholder Engagement section of CEA
V | Launch Initiative V (CTC): Engage Stakeholders and/or Establish Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Robbie Hume, Joey Riddle
| Press Release re: Kentucky RHT funding | 2025-12-29 | 2025-12-29 | Complete | Governor's Office | kentucky.gov/Pages/Activity-stream.aspx?n=GovernorBeshear&prId=2666
| KyRHT appearances before the Kentucky Legislature during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Dr. John Langefeld, Tom Walton
| Project Sponsor and RHT Director testify before the Senate Standing Committee on Health Services | 2026-02-18 | 2026-02-18 | Complete | Dr. John Langefeld, Tom Walton
| RHT Director testifies before the Interim Joint Budget Review Subcommittee of Health and Family Services Committee | 2026-06-03 | 2026-06-03 | Complete | Tom Walton
| RHT Director testifies before the Interim Joint Committee on Health Services | 2026-06-16 | 2026-06-16 | Complete | Tom Walton
| Develop "Jane's Journey" for Crisis to Care Initiative | 2026-02-20 | 2026-03-18 | Complete | Robbie Hume
| Develop 1-page CTC handout for stakeholder meetings and conferences | 2026-04-01 | 2026-05-15 | Complete | Jessi Watts, Robbie Hume | Included in CEA
| CTC Stakeholder Advisory Groups | 2026-01-01 | 2026-07-31 | Complete | Robbie Hume, Joey Riddle | Details provided with Checkpoint Evidence
| CTC Stakeholder Engagement during Reporting Period 1 | 2026-01-01 | 2026-07-31 | Complete | Jessi Watts, Hume and Riddle | Details provided with Checkpoint Evidence
| Initial work planning, team structure, and stakeholder engagement | 2026-01-05 | 2026-03-15 | Complete | Robbie Hume
| Establish CTC Advisory Workgroup charter | 2026-02-02 | 2026-02-02 | Complete | Robbie Hume
| Call for advisory workgroup nominations | 2026-02-16 | 2026-02-16 | Complete | Robbie Hume
| Select EMS agency outreach | 2026-02-02 | 2026-03-13 | Complete | Robbie Hume
| Establish CTC Advisory Workgroup | 2026-03-15 | 2026-03-15 | Complete | Robbie Hume
| Develop RMOCC Workgroup Subcommittee | 2026-06-02 | 2026-06-02 | Complete | Angela Kik
| Establish Subcommittee of the EMS Agency RFAs Workgroup | 2026-05-28 | 2026-05-28 | Complete | Jimmie Hampton
| Develop EMS Agency RFAs Workgroup Subcommittee | 2026-05-28 | 2026-05-28 | Complete | Jimmie Hampton
| Develop Education & Training Modernization Workgroup Subcommittee | 2026-06-12 | 2026-06-12 | Complete | Jimmie Hampton
Stage 2 | Early Scale
| Checkpoint 2.1 Continue initiaitve activities (implementation) |  |  |  |  | Please consider this project plan as evidence for conitinued activites after CTC Initiative Launch
V.a.1 | Select Pilot Agencies for EMS Education & Training (E&T) Modernization (training equipment) | 2026-04-30 | 2026-04-30 | Complete | Jimmie Hampton | Checkpoint 2.2 Achieve at least one post-launch milestone
| Establish training moderanization strategy and scope for EMS workforce and develop RFA | 2026-04-30 | 2026-04-30 | Complete | Jimmie Hampton | Note: E&T modernization is a broad effort suporting all levels of EMS workforce
| RFA for EMS education/training pilot partners launched | 2026-05-11 | 2026-05-11 | Complete | Jimmie Hampton | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| RFA Information Session | 2026-05-21 | 2026-05-21 | Complete | Jimmie Hampton
| RFA Office Hours | 2026-05-27 | 2026-06-08 | Complete | Jimmie Hampton
| Application deadline | 2026-06-12 | 2026-06-12 | Complete | Jimmie Hampton | 42 applications received
| Finalize pilot agencies for EMS E&T modernization | 2026-06-30 | 2026-06-30 | Complete | Jimmie Hampton | 35 applications approved: 25 fixed site equipment grants and 10 mobile equipment grants
| Notification of Award sent to successful applicants | 2026-07-14 | 2026-07-14 | Complete | Jimmie Hampton | Contracts have been submitted and are in final stages of review and approval
V.a.2 | Select Learning Design Organization to develop online Paramedic educational content | 2026-04-02 | 2027-02-05 | In Progress - On Track | Jimmie Hampton
| Develop RFI for Learning Design Organization | 2026-04-02 | 2026-05-28 | Complete | Jimmie Hampton | Note: not part of E&T; specific to paramedic training
| Publish RFI | 2026-05-27 | 2026-05-27 | Complete | Jimmie Hampton
| Response deadline | 2026-08-17 | 2026-08-17 | Not Yet Started | Jimmie Hampton | 4 respondents
| Request presentations from RFI respondents | 2026-08-17 | 2026-08-17 | Not Yet Started | Jimmie Hampton | all 4 respondents invited to present
| Begin RFP process | 2026-09-08 | 2026-11-01 | Not Yet Started | Jimmie Hampton
| Define curriculum scope, requirements, and desired learning outcomes | 2026-10-01 | 2026-11-30 | Not Yet Started | Jimmie Hampton
| Develop and release procurement materials for Learning Design Organization | 2026-11-01 | 2026-11-30 | Not Yet Started | Jimmie Hampton
| Application deadline | 2026-12-30 | 2026-12-30 | Not Yet Started | Jimmie Hampton
| Evaluate proposals | 2027-01-15 | 2027-01-29 | Not Yet Started | Jimmie Hampton
| Select Learning Design Organization to develop online paramedic educational content | 2027-01-29 | 2027-02-05 | Not Yet Started | Jimmie Hampton
V.a.2 | Paramedic educational content finalized | 2026-08-01 | 2027-12-30 | Not Yet Started | Jimmie Hampton
| Establish curriculum development governance | 2026-08-01 | 2027-02-01 | Not Yet Started | Jimmie Hampton
| Finalize curriculum framework and content development roadmap | 2027-06-01 | 2027-12-31 | Not Yet Started | Jimmie Hampton
V.a.4 | Select Health Care Workforce Pipeline Partners | 2026-01-01 | 2026-07-31 | Complete | Ashley Gibson | Checkpoint 2.2 Achieve at least one post-launch milestone
| Select organization(s) to support workforce pipeline in rural areas focusing on KyRHT related positions | 2026-04-01 | 2026-07-31 | Complete | Ashley Gibson | UK contract started 7/1/2026; UofL contract starts 8/1/2026
V.a.4 | Create Clinical Learning Opportunities for Paramedic Students | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Jimmie Hampton
| Establish formal written partnerships with at least two emergency medical services (EMS) agencies and two hospital partners to coordinate and provide clinical learning opportunities for paramedic students | 2026-08-01 | 2027-09-30 | Not Yet Started | Ashley Gibson, Jimmie Hampton
V.b | Select Pilot Agencies to Establish or Expand Community Paramedicine Services | 2026-04-30 | 2026-04-30 | Complete | Jimmie Hampton | Checkpoint 2.2 Achieve at least one post-launch milestone
| Develop Community Paramedicine RFA | 2026-04-30 | 2026-04-30 | Complete | Jimmie Hampton | Note: not part of E&T modernization; prep for IBSC Community Paramedicine (CP-C) exam
| RFA released | 2026-05-01 | 2026-05-01 | Complete | Jimmie Hampton | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| RFA Information Session | 2026-05-08 | 2026-05-08 | Complete | Jimmie Hampton
| Facilitate community paramedicine RFA information session and office hours for EMS agencies | 2026-05-15 | 2026-06-05 | Complete | Jimmie Hampton
| Application deadline | 2026-06-12 | 2026-06-12 | Complete | Jimmie Hampton | 19 applications received
| Finalize pilot agencies for community paramedicine training modernization | 2026-06-13 | 2026-06-30 | Complete | Jimmie Hampton | 16 applications approved
| Notification of Award sent to successful applicants | 2026-07-14 | 2026-07-14 | Complete | Jimmie Hampton | Contracts have been submitted and are in final stages of review and approval
V.c | Select initial cohort of EMS pilot agencies for TNT/TAD Services | 2026-03-15 | 2026-07-14 | Complete | Jimmie Hampton | Checkpoint 2.2 Achieve at least one post-launch milestone
| Develop RFA for TNT/TAD pilot partners | 2026-03-15 | 2026-05-15 | Complete | Jimmie Hampton
| RFA released | 2026-05-15 | 2026-05-15 | Complete | Jimmie Hampton | RFA materials posted at https://ruralhealthplan.ky.gov/Pages/Request_For_Applications.aspx
| RFA information session | 2026-05-28 | 2026-05-28 | Complete | Jimmie Hampton
| Facilitate TNT/TAD office hours for EMS agencies | 2026-06-02 | 2026-06-10 | Complete | Jimmie Hampton
| Application deadline | 2026-06-15 | 2026-06-15 | Complete | Jimmie Hampton | 5 applications received
| Finalize pilot agencies for TNT/TAD transformation | 2026-07-07 | 2026-07-13 | Complete | Jimmie Hampton | 3 applications approved
| Notification of Award sent to successful applicants | 2026-07-14 | 2026-07-14 | Complete | Jimmie Hampton | Contracts have been submitted and are in final stages of review and approval
V.c | Co-develop statewide TNT and TAD implementation strategies and protocols with pilot EMS agencies and KBEMS | 2026-07-13 | 2026-12-31 | In Progress - On Track | Julia Deboor
| Collect best implementation ideas from TNT/TAD applications | 2026-07-13 | 2026-07-31 | Complete | Julia Deboor
| Define TNT/TAD priority use cases (behavioral health, low-acuity medical, alternate destination pathways) | 2026-07-13 | 2026-07-31 | Complete | Julia Deboor
| Establish roadmap for codevelopment of TNT and TAD clinical protocols and implementation guidance | 2026-07-13 | 2026-09-30 | In Progress - On Track | Julia Deboor
| Train pilot agencies on TNT/TAD implementation protocols | 2026-09-01 | 2026-10-30 | Not Yet Started | Julia Deboor
| Draft TNT and TAD clinical protocols and implementation guidance | 2026-07-13 | 2026-11-30 | In Progress - On Track | Julia Deboor
| Review and refine protocols with KBEMS, medical directors, and key stakeholders | 2026-08-01 | 2026-11-30 | Upcoming | Julia Deboor
| Submit protocols to KBEMS for their approval process | 2026-11-30 | 2026-11-30 | Upcoming | Julia Deboor
V.c | Pilot TNT/TAD implementation strategies with initial EMS agency cohort | 2026-11-30 | 2027-05-01 | Not Yet Started | Julia Deboor
| Deploy TNT/TAD workflows across pilot agencies | 2026-11-30 | 2026-12-31 | Not Yet Started | Julia Deboor
| Monitor TNT/TAD utilization and operational performance | 2026-10-01 | 2027-04-01 | Not Yet Started | Julia Deboor
| Collect implementation feedback from pilot agencies | 2026-11-01 | 2027-02-01 | Not Yet Started | Julia Deboor
| Refine TNT/TAD strategies based on pilot results | 2027-02-01 | 2027-05-01 | Not Yet Started | Julia Deboor
V.d | Finalize business requirements for EMS integrated care communication technology | 2026-02-02 | 2026-06-22 | Complete | Angela Kik | Checkpoint 2.2 Achieve at least one post-launch milestone
| Align with UK and UofL on RMOCC implementation timeline, operating model, and startup requirements | 2026-02-02 | 2026-02-16 | Complete | Angela Kik
| Facilitate requirements to define RMOCC coordination workflows and technology needs | 2026-02-16 | 2026-02-23 | Complete | Angela Kik
| Refine recommendation for EMS-integrated care communication technology | 2026-03-02 | 2026-05-15 | Complete | Angela Kik
| Develop RMOCC organizational structure and staffing plan | 2026-05-01 | 2026-05-29 | Complete | Angela Kik
| Vendor cleared CHFS technology security review | 2026-06-01 | 2026-06-11 | Complete | Angela Kik
| Determine governance and ownership of dispatch coordination technology | 2026-06-15 | 2026-06-15 | Complete | Angela Kik
| Technology partner notified of selection | 2026-06-22 | 2026-06-22 | Complete | Angela Kik | Contract is currently under review by the CHFS Office of Legal Services
V.d | Onboard initial EMS agencies and acute care facilities onto EMS communication technology | 2026-09-01 | 2027-03-01 | Not Yet Started | Angela Kik
| Onboard initial EMS agencies to communication technology | 2026-09-01 | 2027-03-01 | Not Yet Started | Angela Kik
| Onboard initial acute care facilities to communication technology | 2026-09-01 | 2027-03-01 | Not Yet Started | Angela Kik
| Configure technology access and user permissions | 2026-09-01 | 2027-03-01 | Not Yet Started | Angela Kik
| Train participating organizations on platform workflows | 2026-09-01 | 2027-03-01 | Not Yet Started | Angela Kik
| Activate technology use for initial pilot participants | 2026-09-15 | 2026-12-31 | Not Yet Started | Angela Kik
V.e | Select lead organization for STARS program in Kentucky | 2026-03-15 | 2026-03-15 | Complete | Angela Kik | Checkpoint 2.2 Achieve at least one post-launch milestone
| Confirm lead organization for STARS program | 2026-03-15 | 2026-03-15 | Complete | Angela Kik | Norton Children's Hospital
| Align with UofL on STARS program launch timeline | 2026-03-15 | 2026-03-15 | Complete | Angela Kik | MOA is in the final stages of review and approval
V.e | Onboard the first cohort of EMS agencies supporting STARS | 2026-09-01 | 2026-12-31 | Not Yet Started | Angela Kik
| Recruit initial EMS agencies for STARS participation | 2026-08-15 | 2026-09-30 | Not Yet Started | Angela Kik
| Execute participation agreements with STARS agencies | 2026-08-15 | 2026-09-30 | Not Yet Started | Angela Kik
| Train agencies on STARS program requirements | 2026-09-01 | 2026-12-31 | Not Yet Started | Angela Kik
| Launch STARS services within participating agencies | 2026-09-15 | 2026-12-31 | Not Yet Started | Angela Kik
| Monitor agency participation and program adoption | 2026-09-15 | 2027-06-30 | Not Yet Started | Angela Kik
Checkpoint 2.3 Establish Reporting Methodology
| Submit Metric Reporting Methodology Report to CMS | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
| Develop finalized metric approaches including how methodologies are being implemented in practice | 2026-05-01 | 2028-06-30 | In Progress - On Track | Dr. Sarah Lewis
Checkpoint 2.4 Submit updated project plan to CMS
| Updated Project Plan sent to CMS | 2026-11-01 | 2028-05-30 | Not Yet Started | Andrea Adams
Stage 3 | Implementation Mid-point 2Q28
Checkpoint 3.1 Receive CMS approval of updated project plan
| Updated Project Plan Approved by CMS | 2028-06-01 | 2028-06-30 | Not Yet Started | CMS
Checkpoint 3.2 Complete 2Q28 milestones
V.a.2 | Develop community paramedicine guidance materials to demonstrate best practices and standardize reporting across Kentucky | 2027-07-01 | 2028-06-30 | Not Yet Started | Julia Deboor
V.a.2 | Expand access to community paramedicine programs, ensuring at least one program in every geographic region in the state | 2027-07-01 | 2028-06-30 | Not Yet Started | Julia Deboor
Checkpoint 3.3 Report Initial Metric Progress to CMS
| Initial Metric Progress and/or Reporting Methods Report sent to CMS | 2028-07-01 | 2028-12-30 | Not Yet Started | Dr. Sarah Lewis
Stage 4 | Near Completion
V.a.1 | Begin pilot testing Paramedic didactic curriculum with early adopters and integrate feedback | 2028-07-01 | 2029-06-30 | Not Yet Started | Jimmie Hampton | `
V.a.1 | Finalize pilot testing of Paramedic didactic educational content and promote the training program to agencies | 2029-07-01 | 2030-06-30 | Not Yet Started | Jimmie Hampton
V.a.2 | Expand access to community paramedicine programs, targeting at least two programs in every geographic region in the state | 2029-07-01 | 2030-06-30 | Not Yet Started | Julia DeBoor
V.b | Release statewide TNT/TAD guidance and launch technical assistance program to support implementation | 2028-07-01 | 2029-06-30 | Not Yet Started | Julia DeBoor
V.b | Develop a sustainability framework strategy to support TNT/TAD and community paramedicine | 2029-07-01 | 2030-06-30 | Not Yet Started | Julia DeBoor
V.c | Operationalize RMOCC, including infrastructure, governance, core technology, and initial EMS and acute care facility participation with a regional or scope focus | 2029-07-01 | 2030-06-30 | Not Yet Started | Angela Kik
| Complete statewide policy and regulatory review. | 2028-07-01 | 2029-06-30 | Not Yet Started | Julia DeBoor
| Identify state-level barriers and recommended solutions to support TNT/TAD and community paramedicine | 2028-07-01 | 2029-06-30 | Not Yet Started | Julia DeBoor
| Complete Initial CTC Program Evaluation | 2028-01-01 | 2028-09-30 | Not Yet Started | Dr. Sarah Lewis, Joey Riddle
Checkpoint 4.1 Share final deliverables plan with CMS
|  | 2028-07-01 | 2029-03-31 | Not Yet Started | Andrea Adams
Checkpoint 4.2 CMS approval of final deliverables plan
|  | 2029-04-01 | 2029-04-30 | Not Yet Started | CMS
Checkpoint 4.3 Complete post-program planning
|  | 2029-05-01 | 2030-06-30 | Not Yet Started | Leadership Team
Stage 5 | Fully Implemented
V.a.1 | Online Didactic Paramedic curriculum incorporated into at least 15% of Level 4 TEI agencies throughout the Commonwealth | 2030-07-01 | 2030-10-30 | Not Yet Started | Jimmie Hampton
V.a.1 | Release paramedic didactic content for initial cohorts (integrated with skills sites) and graduate first cohort | 2030-07-01 | 2030-10-30 | Not Yet Started | Jimmie Hampton
V.b | Finalize the ongoing sustainability framework strategies to support TNT/TAD and community paramedicine and distribute to EMS agencies | 2030-07-01 | 2030-10-30 | Not Yet Started | Julia DeBoor
V.c | Expand the RMOCC scale to include one additional region or scope focus | 2030-07-01 | 2030-10-30 | Not Yet Started | Angela Kik
V | Complete Final CTC Program Evaluation | 2030-07-01 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Joey Riddle
Checkpoint 5.1 Submit final deliverables to CMS
V | Final deliverables completed and submitted to CMS | 2030-07-01 | 2031-02-27 | Not Yet Started | Andrea Adams
Checkpoint 5.2 Complete all 2030 milestones
V | All CTC 2030 milestones are complete | 2030-07-01 | 2030-07-31 | Not Yet Started | Joey Riddle
Checkpoint 5.3 Report updated metric progress to CMS
V | Updated metric progress report sumitted to CMS | 2030-10-30 | 2030-12-15 | Not Yet Started | Dr. Sarah Lewis, Joey Riddle
| Submit Final Report to CMS | 2030-10-30 | 2031-02-27 | Not Yet Started | Andrea Adams
Formulas:
Target Due Date = MAX([Target Due Date, row below]:D98)
Target Start = MIN([Target Start, row below]:C119)